DELHI DEVELOPMENT AUTHORITY

# ELECTRICAL DIVISION – 2

ELECTRICAL CIRCLE -I

List of Activities:-

1.	Detail of pending final bills of non refund of security deposits :-

As on 01/08/07

| S. No. | Name of Scheme | Agreement No. | Agency | Remarks |
| --- | --- | --- | --- | --- |
|  | ----- NIL ----- |  |  |  |

2.	Progress of Works

## 2A.	Progress of works costing of more than 30 lakhs

As on 01/08/2007

| S. No. | Name of Scheme | Estt. / Tender Cost | Agreement No. | Agency | Date of Start Time of comp. (Period) | Supplementary Agent if Drawnn | Physical ____% of Allotment | Present Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

NIL

| 2B. Progress of works costing of more than 2 Lakhs & less than 30 Lakhs As on 01/08/2007 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S. No. | Name of Scheme | Estt. / Tender Cost | Agreement No. | Agency | Date of Start Time of comp. (Period) | Supplementary Agent if Drawnn | Physical ____% of Allotment | Present Status |
| 1. | C/o 384 SFS houses in Pkt 1& 2, Sec 3, Dwarka, Phase II |  |  |  |  |  |  |  |
| (a) | IEI of 120 SFS Cat. II + 72 SFS Cat III & 144 Scooter Garages in Gr. II | 1600316.00 1647845.00 | 83/ED-2/92-93 | S. K. Const. Pvt. Ltd. | 7.1.93 30 months | Drawn in 95-96 | 90% | Under Allotment |
| (b) | I.E.I. of 120 SFS Cat II + 72 SFS Cat III & 144 Scooter Garage in Gr. II | 1600316.00 1647845.00 | 84/ED-2/92-93 | S. K. Const. Pvt. Ltd. | 7.1.93 30 months | Drawn in 95-96 | 85% | Under Allotment |
| 2. | C/o 456 (342 MIG + 144 LIG Four storyed & 342 scooter garage. |  |  |  |  |  |  |  |
| (a) | I.E.I. 126 MIG + 42 LIG & 126 Scooter garage in Gr. I | 1013068.00 1087022.00 | 113/ED-2/92-93 | S. K. Const. Pvt. Ltd. | 1.4.93 30 months | Drawn in 95-96 | 85% | Under Allotment |
| (b) | IEI of 120 MIG & 42 LIG & 120 Scooter garge in Gr. II | 964739.00 1035165.00 | 114/ED-2/92-93 | S. K. Const. Pvt. Ltd. | 1.4.93 30 months | Drawn in 95-96 | 88% | Under Allotment |
| (c) | I.E.I. of 96 MIG & 32 LIG & 96 scooter garage in Gr. III | 771672.00 828004.00 | 115/ED-2/92-93 | S. K. Const. Pvt. Ltd. | 1.4.93 30 months | Drawn in 95-96 | 88% | Under Allotment |

As on 01/08/2007

| S. No. | Name of Scheme | Estt. / Tender Cost | Agreement No. | Agency | Date of Start Time of comp. (Period) | Supplementary Agent if Drawnn | Physical ____% of Allotment | Present Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3. | 2693/2714 EWS & 358/376 LIG Dus in Pkt 3 Bindapur |  |  |  |  |  |  |  |
| (i) | 240 EWS + 40 LIG BLK D III Pkt 3, Bindapur | 518211.00 644914.00 | 131\ED-2\91-92 | M/s Metro Elect. Co. | 15.2.92 30 Months | Drawn in 95-96 | 50% | Under Allotment |
| (ii) | 268 EWS + 36 LIG blk B-1, Pkt 3, Bindapur | 651313.00 692334.00 | 132\ED-2\91-92 | M/s Metro Elect. Co. | 15.2.92 30 Months | Drawn in 95-96 | 52% | Under Allotment |
| (iii) | 278 EWS + 40 LIG blk D-1, Pkt 3, Bindapur | 583695.00 726408.00 | 133\ED-2\91-92 | M/s Metro Elect. Co. | 15.2.92 30 Months | Drawn in 95-96 | 45% | Under Allotment |
| (iv) | 282 EWS +23 LIG blk DII, Pkt 3, Bindapur | 629711.00 763675.00 | 134\ED-2\91-92 | M/s Metro Elect. Co. | 15.2.92 30 Months | Drawn in 95-96 | 47% | Under Allotment |
| (v) | 309 EWS + 32 LIG blk A Pkt 3 Bindapur | 616521.00 767260.00 | 135\ED-2\91-92 | M/s Metro Elect. Co. | 15.2.92 30 Months | Drawn in 95-96 | 60% | Under Allotment |
| (vi) | 284 EWS +36 LIG blk B II Pkt 3 Bindapur | 584094.00 726909.00 | 136\ED-2\91-92 | M/s Metro Elect. Co. | 15.2.92 30 Months | Drawn in 95-96 | 60% | Under Allotment |
| (vii) | 280 EWS + 36 LIG blk E III Pkt 3 Bindapur | 547863.00 681816.00 | 137\ED-2\91-92 | M/s Metro Elect. Co. | 15.2.92 30 Months | Drawn in 95-96 | 40% | Under Allotment |
| (viii) | 255 EWS + 55 LIG blk E II Pkt 3 Bindapur | 557169.00 693397.00 | 116\ED-2\91-92 | M/s H.O. Elect. | 15.2.92 30 Months | Drawn in 95-96 | 45% | Under Allotment |
| (ix) | 113 EWS + 20 LIG blk B III Pkt 3, Bindapur | 227362.00 282958.00 | 142\ED-2\91-92 | M/s Shaka Electric | 15.2.92 30 Months | Drawn in 95-96 | 36% | Under Allotment |
| (x) | 220 EWS + 20 LIG blk B III, Pkt 3, Bindapur | 430340.00 | 56\ED-2\04-05 | M/s Metro Elect. Co. | 03.04.05 12 Months | Rescinded works | 50% | Under Allotment |
| (xi) | 202 EWS + 24 LIG blk B III Pkt 3 , Bindapur | 400015.00 | 57\ED-2\04-05 | M/s Metro Elect. Co. | 03.04.05 12 Months | Rescinded works | 40% | Under Allotment |
| (xii) | C/o 224 Janta & 55 LIG Dus at Isolated Pkt 10, Naseerpur | 837922.00 862641.00 | 23\ED-2\92-93 | M/s Metro Elect. Co. | 12.06.92 30 Months | Drawn in 95-96 | 77% | Under Allotment |

As on 01/08/2007

| S. No. | Name of Scheme | Estt. / Tender Cost | Agreement No. | Agency | Date of Start Time of comp. (Period) | Supplementary Agent if Drawnn | Physical ____% of Allotment | Present Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4. | 470 (198 MS & 272 MIG Pkt 8, Sector 12, Dwarka |  |  |  |  |  |  |  |
| (i) | 128 MIG dus Gr. I | 1853140.00 1446045.00 | 9\ED-2\2002-3 | M/s Bharat Elect. Co. | 20/5/02 12 Months | Not | 91% | Completion recorded |
| (ii) | 144 MIG Dus Gr. II | 2084981.00 1626924.00 | 10\ED-2\2002-3 | M/s Bharat Elect. Co. | 20/5/02 24 Months | Not | 92% | Completion recorded |
| 5. | C/o 208 LIG at Pkt GH3 in G-17, Paschim Vihar | 908524.00 1820316.00 | 44\EE\ED-4\2006-7 | M/s Metro Electric Co. | 26/11/06 9 Months | Rescinded works | 70% | Under Allotment |
| 6. | C/o 240 MIG near Madipur Village | 2872970.00 .00 | 27\EE\ED-4\2001-2 | M/s Goel Electircals | 30/10/01 36 Months | Not | 81% | Under Allotment |
| 7. | Staff quarters at A-5, Paschim Vihar | 199480.00 217324.00 | 166\EE\ED-2\2004 -05 | M/s Ram Gopal & Co. | 03/04/05 3 Months | Not | 33% | Under Allotment |

2C.	Annual Running & Maintenance of Booster Pumping Sets

and others Works Electrical Division – II

As on 01/08/2007

| S. No. | Name of Scheme |  | Estt./Tender Cost | Agreement No. | Agency | Date of Start Time of comp. | Status of Tube Well |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Dwarka Zone |  |  |  |  |  |  |  |
| 1. | Street lighting at 60 mtr. Wide Road Phase – 1, Dwarka. |  | 630098.00 438779.00 | 24/EE/ED-2 2006-07 | M/s. N.K. Engineering Works | 21/10/06 01/10/07 | - |
| 2. | Street lighting at 60 mtr. Wide Road Phase – 2, Dwarka. |  | 653998.00 443924.00 | 22/EE/ED-2 2006-07 | M/s. N.K. Engineering Works | 28/06/06 27/09/07 | - |
| Sector – 2, Dwarka |  |  |  |  |  |  |  |
| 3. | M/s. Booster Pump Set i/c D.G. Set at 136/208 M.I.G., L.I.G., Pkt. 1, Sector - 2. |  | 162615.00 158500.00 | 44/EE/ED-2 2006-07 | M/s. Hindustan Enterprises | 30/01/07 29/01/08 | No |
| 4. | M/s. Booster Pump Set i/c D.G. Set at 80/106 M.I.G., L.I.G., Pkt. 2, Sector - 2. |  | 166469.00 160710.00 | 11/EE/ED-2 2007-08 | M/s. Hindustan Enterprises | 03/05/07 02/05/08 | Tube Well Functional |
| Sector – 3, Dwarka |  |  |  |  |  |  |  |
| 5. |  | M/o Clear Water Booster P/Set i/c D.G. Set at 384 SFS, Pkt.1 & 2, Sector – 3. | 166523.00 160750.00 | 48/EE/ED-9 2006-07 | M/s. Industrial Engg. Works | 22/03/07 21/03/08 | No |
| 6. |  | M/o Clear Water Booster P/Set i/c D.G. Set at 608 L.I.G. & M.I.G., Pkt. 16, Sector – 3. | 162127.00 141323.00 | 28/EE/ED-2 2006-07 | M/s. Pumps Engg. & Associates | 08/10/06 07/10/07 | No |
| 7. |  | M/o Storm Water P/Set i/c D.G. Set at Sector – 3. | 165336.00 157800.00 | 10/EE/ED-2 2007-08 | M/s. Prominent Electronic Works | 17/06/07 16/06/08 | No |
| Sector – 5, Dwarka |  |  |  |  |  |  |  |
| 8. |  | M/o Intercom System at Division Office, Sector – 5. | 69952.00 28800.00 | /EE/ED-2 2007-08 | M/s. W.S. Telematrices Pvt. Ltd. | 27/07/07 26/07/08 | - |
| Sector – 6, Dwarka |  |  |  |  |  |  |  |
| 9. |  | M/o Clear Water Booster P/Set i/c D.G. Set at 456 M.I.G., Pkt. 2, Sector – 6. | 162615.00 157220.00 | 38/EE/ED-2 2006-07 | M/s. Hindustan Entperises | 06/01/07 05/01/08 | No |

As on 01/08/2007

| S. No. | Name of Scheme |  | Estt./Tender Cost | Agreement No. | Agency | Date of Start Time of comp. | Status of Tube Well |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sector – 7, Dwarka |  |  |  |  |  |  |  |
| 10. | M/o Clear Water Booster P/Set i/c D.G. Set at 182 SFS Pkt.1, Sector – 7. |  | 162615.00 157220.00 | 39/EE/ED-2 2006-07 | M/s. Hindustan Enterprises | 06/01/07 05/01/08 | Tube Well Abandoned |
| 11. | M/o Clear Water Booster P/Set i/c D.G. Set at 452 MIG, LIG & Janta, Pkt. 2, Sector – 7. |  | 166523.00 160750.00 | 49/EE/ED-2 2006-07 | M/s. Dhaliwal Engg. Works | 22/03/07 21/03/08 | No |
| Sector – 11, Dwarka |  |  |  |  |  |  |  |
| 12 | M/o Submersible Pump i/c D.G. Set T – 5, T – 6, Sector – 11. |  | 213600.00 192000.00 | 29/EE/ED-2 2006-07 | M/s. Hindustan Enterprises | 14/11/06 13/07/07 | Supply to 333 Du’s Pkt. 2, Sector 12 |
| Sector – 12, Dwarka |  |  |  |  |  |  |  |
| 13. |  | M/o Clear Water Booster P/Set i/c D.G. Set at 333 Du’s, Pkt. 2, Sector – 12. | 165509.00 159050.00 | 45/EE/ED-2 2006-07 | M/s. Hindustan Enterprises | 10/02/07 09/02/08 | No |
| 14. |  | M/o Clear Water Booster P/Set i/c D.G. Set at 470 Du’s, Pkt. 8, Sector – 12. | 349500.00 339000.00 | 15/EE/ED-2 2006-07 | M/s. N.K. Engg. Works | 27/07/06 26/07/07 | No |
| 15. |  | M/o Lifts at 198 HIG, Pkt. 8, Sector – 12. | 752400.00 752400.00 | 11/EE/ED-9 2007-08 | M/s. Otis Elevator Co. | 18/06/07 17/06/08 | - |
| 16. |  | O/M of Lifts at 198 HIG, Pkt. 12, Sector – 12. | 880416.00 840000.00 | 8/EE/ED-2 2006-07 | M/s. Sudhir Electrical | 12/06/06 11/06/07 | - |
| 17. |  | M/o Submersible P/Set i/c D.G. Set T – 15 at Pkt. 1, Sector – 12. | 167715.00 164150.00 |  | M/s. Satkar Electricals | 20/07/07 19/07/08 | Supply to 452 Du’s Pkt. 1, Sector 12 |
| Sector – 18, Dwarka |  |  |  |  |  |  |  |
| 18. |  | M/o Clear Water Booster P/Set i/c D.G. Set at Veer Vyas Yozna, Sector – 18A. | 168864.00 59400.00 | 13/EE/ED-2 2007-08 | M/s. Hindustan Enterprises | 25/06/07 24/06/08 | No |
| Sector – 24, Dwarka |  |  |  |  |  |  |  |
| 19. |  | O/M of Pumping Set SPS No. 3, Sector – 24. | 304446.00 164900.00 | 43/EE/ED-2 2006-07 | M/s. Trehan Enterprises | 10/02/07 09/08/07 | No |

As on 01/08/2007

| S. No. | Name of Scheme |  | Estt./Tender Cost | Agreement No. | Agency | Date of Start Time of comp. | Status of Tube Well |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 20. | Providing Gun Man for Security for Electrical, Mechanical & Civil Installation at SPS No. 3, Sector - 24. |  | 242352.00 241200.00 | 30/EE/ED-2 2006-07 | M/s. High Command | 19/11/06 18/11/07 | No |
| bindapur |  |  |  |  |  |  |  |
| 21. | Clear Water Booster P/Set i/c D.G. Set P/House No. 1, Bindapur. |  | 172200.00 154800.00 | 34/EE/ED-2 2006-07 | M/s. Hindustan Enterprises | 09/12/06 08/12/07 | No |
| 22. | Clear Water Booster P/Set i/c D.G. Set P/House No. 2, Bindapur. |  | 173388.00 168000.00 | 9/EE/ED-2 2007-08 | M/s. Dhaliwal Engg. Works | 22/07/07 21/07/08 | No |
| 23. | Sewage Pumping Set at Pkt. 3, Bindapur. |  | 165336.00 159600.00 | 50/EE/ED-2 2006-07 | M/s. Hindustan Enterprises | 22/03/07 21/03/08 | No |
| 24. | Storm P/Set at Pkt. 3, Bindapur. |  | 167760.00 156000.00 | 55/EE/ED-2 2006-07 | M/s. Hindustan Enterprises | 25/12/06 24/12/07 | No |
| Nasirpur |  |  |  |  |  |  |  |
| 25. |  | O/M of Clear Water Booster P/Set i/c D.G. Set at 208 Janta, Pkt. 6. | 170696.00 168380.00 | 7/EE/ED-9 2007-08 | M/s. Gurnam Bros. | 11/06/07 10/06/08 | Tube Well Functional |
| 26. |  | O/M of Clear Water Booster P/Set i/c D.G. Set at 272, Janta, Pkt. 6. | 170696.00 168380.00 | 16/EE/ED-9 2007-08 | M/s. Kuka Enterprises | 23/07/07 22/07/08 | - do - |
| 27. |  | O/M of Clear Water Booster P/Set i/c D.G. Set at 472, Janta, Pkt. 6. | 167602.00 95260.00 | 3/EE/ED-2 2007-08 | M/s. Gurnam Bros. | 26/05/07 25/05/08 | - do - |
| 28. |  | O/M of Clear Water Booster P/Set i/c D.G. Set at 256, Janta, Pkt. 6. | 170696.00 170696.00 | 8/EE/ED-2 2007-08 | M/s. Gurnam Bros. | 11/06/07 10/06/08 | - do - |
| 29. |  | O/M of Clear Water Booster P/Set i/c D.G. Set at 328, Janta, Pkt. 6/2. | 165000.00 162000.00 | 17/EE/ED-2 2006-07 | M/s. Hindustan Enterprises | 11/08/07 31/07/08 | - do - |

As on 01/08/2007

| S. No. | Name of Scheme |  | Estt./Tender Cost | Agreement No. | Agency | Date of Start Time of comp. | Status of Tube Well |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 30. | O/M of Clear Water Booster P/Set i/c D.G. Set at 280 Janta, Pkt. 6/3. |  | 164535.00 158500.00 | 44/EE/ED-2 2006-07 | M/s. Prominent Elect. Works | 10/12/07 09/12/08 | - do - |
| 31. | Sewage Pumping Set i/c Diesel Engine at Pkt. 6/3. |  | 161244.00 157200.00 | 42/EE/ED-2 2006-07 | M/s. Dhaliwal Engg. Works | 04/02/07 03/02/08 | No |
| 32. | O/M of Clear Water Booster P/Set i/c D.G. Set & Sewage Pump Set at 560 Janta, Pkt. 7, Nasirpur. |  | 168540.00 162000.00 | 18/EE/ED-2 2006-07 | M/s. Gurnam Bros. | 06/08/06 05/08/07 | Tube Well Functional |
| 33. | O/M Submersible P/Set, Pkt. 8, Nasirpur. |  | 163680.00 159600.00 | 16/EE/ED-2 2006-07 | M/s. Hindustan Enterprises | 01/08/06 30/07/07 | Functional |
| 34. | O/M of Clear Water Booster P/Set & D.G. at 174 EWS & 68 L.I.G., Pkt. 9, Narispur. |  | 167602.00 161800.00 | 51/EE/ED-2 2006-07 | M/s. Dhariwal Engg. Works | 09/04/07 08/04/08 | Tube Well Abandoned |
| 35. | O/M of Clear Water Booster P/Set & D.G. at 124 Janta & 55 L.I.G., Pkt. 10, Narispur. |  | 162615.00 158250.00 | 46/EE/ED-2 2006-07 | M/s. Hindustan Enterprises | 10/02/07 09/02/08 | - do - |
| 36. | O/M of Clear Water Booster P/Set & D.G. at 808 Janta, Pkt. 13, Nasirpur. |  | 163363.00 143462.00 | 26/EE/ED-2 2006-07 | M/s. Lloyds Enterprises | 08/10/06 07/10/07 | Tube Well Functional |
| Janakpuri |  |  |  |  |  |  |  |
| 37. |  | M/o Lifts at Plot No. 2 & 5 at Distt. Centre, Janakpuri. | 2171880.00 2233160.00 | 18/EE/ED-2 2007-08 | M/s. Olympics Elevator Pvt. Ltd. | 29/07/07 28/07/08 | N/A |
| 38. |  | R/o of Lifts in Plot No. 1, 2 & 5 at Distt. Centre, Janakpuri. | 441984.00 450000.00 | 27/EE/ED-2 2007-08 | M/s. Sky Park (India) Elevator Co. | 05/10/06 04/10/07 | N/A |
| 39. |  | O/M Fire Services, D.G. Sets, Elevator Booster P/Set & Common Light in Plot No. 1, 2, 5 & 7A, Distt. Centre, Janakpuri. | 984312.00 979200.00 | 48/EE/ED-2 2007-08 | M/s. N.K. Engg. Works | 29/05/07 25/05/08 | N/A |

As on 01/08/2007

| S. No. | Name of Scheme | Estt./Tender Cost | Agreement No. | Agency | Date of Start Time of comp. | Status of Tube Well |
| --- | --- | --- | --- | --- | --- | --- |
| Hastal |  |  |  |  |  |  |
| 40. | M/O of Street Light & Submersible P/Set at Hastal. | 364572.00 335400.00 | 34/EE/ED-2 2006-07 | M/s. Pump Engg. & Associates | 02/12/06 01/12/07 | Submersible Pump Set Functional |
| paschim vihar |  |  |  |  |  |  |
| 41. | O/M for Clear Water Booster P/Set i/c D.G. Set at 304 M.I.G., Opp. Naginlake, Paschim Vihar. | 168684.00 165300.00 | 43/EE/ED-2 2007-08 | M/s. Pump Engg. & Associates | 29/04/07 28/04/08 | No |
| 42. | O/M of Clear Water Booster P/Set i/c D.G. Set at 60 CSP Janta Houses, Miya Wali, Paschim Vihar. | 168684.00 165300.00 | 42/EE/ED-2 2007-08 | M/s. Pump Engg. & Associates | 29/04/07 28/04/08 | No |
| 43. | O/M of Clear Water Booster P/Set i/c D.G. Set at 208 L.I.G., Pkt. GH 3, Paschim Vihar. | 166536.00 153000.00 | 33/EE/ED-2 2007-08 | M/s. Pump Engg. & Associates | 23/10/06 22/10/07 | No |

2D.	List of Running Contracts in Force of Horticulture Div. 8

As on 01/08/2007

| S. No. | Name of Work/Park | Estt. Cost/ Net Tender Cost | Agreement No. | Agency | Date of Start/ Date of Completion | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | A.R.M.O. of Pumps + Park lights of A Block Distt. Park, (Narang Colony). | 53900/- | 31/EE/D2 2007-08 | M/s. S.K. Enterprises | 12/10/06 11/10/07 |  |
| 2. | A.R.M.O. of Pumps + Park lights at Salwage Park, Maya Puri. | 83449/- | 23/EE/D2 2007-08 | M/s. S.K. Enterprises | 28/04/06 27/04/07 |  |
| 3. | A.R.M.O. of Pumps + Park lights of Fateh Nagar + G+8, Area Tihar Lake. | 170520/- | /EE/D2 2007-08 | M/s. Rohit Enterprises | 06/10/06 05/10/07 |  |
| 4. | A.R.M.O. of Pumps + Park lights at Parshuram Park, Hari Nagar. | 65688/- | /EE/D2 2007-08 | M/s. R.P. Electric Co. | 26/05/06 25/05/07 |  |
| 5. | A.R.M.O. of Pumps + Park lights at Udham Singh Nagar, Hari Nagar. | 103809/- | 32/EE/D2 2007-08 | M/s. Rishu Construction | 13/10/06 12/10/07 |  |
| 6. | A.R.M.O. of Pumps + Park light at Distt. Park B Block, Janak Puri. | 97370/- | 30/EE/D2 2007-08 | M/s. Rishu Construction | 06/10/06 05/10/07 |  |
| 7. | A.R.M.O. of Pumps + Park lights at LIG + MIG, Rajouri Garden. | 101296/- 90780/- | /EE/D2 2007-08 | M/s. Gurnam Bros. | 23/06/06 22/06/07 |  |
| 8. | A.R.M.O. of Pumps + Park lights at L Shape Park + Babawala + Bb Block, Kargil. | 224064/- 143460/- | /EE/D2 2007-08 | M/s. Kuka Enterprises | 20/04/07 19/04/07 |  |
| 9. | Repair/Rewinding of Pumps Sets in various parks under H.D. No. 8. | 307859/- | 47/EE/D2 2007-08 | M/s. Cholia Electric Works | 11/05/07 10/05/08 |  |
| 10. | M/O Path lights of 30 Nos. Parks pertaining to H.D. 8. | 515684/- 500185/- | 38/EE/D2 2007-08 | M/s. Cholia Electric Works | 16/03/07 15/04/08 |  |
| 11. | S/R of accessories of Control Panel board of pump sets/feeder pillars under H.D. 8. | 224898/- 198740/- | /EE/D2 2007-08 | M/s. Gurnam Bros. | 20/11/06 19/11/07 |  |

2D.	List of Running Contracts in Force of Horticulture Div. 3

As on 01/08/2007

| S. No. | Name of Work/Park | Estt. Cost/ Net Tender Cost | Agreement No. | Agency | Date of Start/ Date of Completion | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | R.M.O. of Pump Sets & Park lights in DDA Park at Tagore Garden & Shivaji Park. | 198022/- 131059/- | /EE/D2 2007-08 | M/s. Ram Gopal & Co. | 26/06/07 28/06/08 |  |
| 2. | R.M.O. of Pump Sets & Park lights in DDA Park at B Block Paschim Vihar Puri, B Block Paschim Vihar. | 66464/- 49500/- | 26/EE/D2 2007-08 | M/s. Rohit Enterprises | 22/08/06 21/08/07 |  |
| 3. | R.M.O. of Pump Sets & Park lights in DDA Park at A Block DG-2 & Nalanda, Vikas Puri. | 157540/- 99460/- | 29/EE/D2 2007-08 | M/s. Pump Engg. & Associates | 06/10/06 05/10/07 |  |
| 4. | R.M.O. of Pump Sets & Park lights in DDA Park at Bhagwati Talab + Madipur. | 112240/- 74480/- | 25/EE/D2 2007-08 | M/s. Rohit Enterprises | 22/08/06 21/08/07 |  |
| 5. | R.M.O. of Pump Sets & Park lights in DDA Park at Picnic Hut, Paschim Vihar + Peera Garhi. | 182968/- 106000/- | 24/EE/D2 2007-08 | M/s. Rohit Enterprises | 14/08/06 13/08/07 |  |
| 6. | R.M.O. of Pump Sets & Park lights in DDA Park at Keshopur Jheel + Antirksh Appt. | 112507/- 110250/- | 40/EE/D2 2007-08 | M/s. Pump Engg. & Associates | 12/04/07 11/04/08 |  |
| 7. | R.M.O. of Pump Sets & Park lights in DDA Park at M Block, C Block, Vikas Puri. | 214261/- 209860/- | 39/EE/D2 2007-08 | M/s. Pump Engg. & Associates | 16/03/07 15/03/08 |  |
| 8. | R.M.O. of Pump Sets & Park lights in DDA Park at Miya Wali Nagar. | 107205/- 105060/- | 41/EE/D2 2007-08 | M/s. H.S. Engg. Works | 12/04/07 11/04/08 |  |
| 9. | Repairing, Rewinding i/c lifting/lowering of Sub. P/Sets situated at different parks pertaining to Hort, Divn. No. 3. | 364416/- 353455/- | /EE/D2 2007-08 | M/s. Pump Engg. & Associates | 10/07/07 09/07/08 |  |
| 10. | M/O Path/Park Lights in 28 Nos. of Parks pertaining to Hort. Div. No. 3 | 485363/- 470890/- | 45/EE/D2 2007-08 | M/s. Rohit Enterprises | 07/05/07 06/05/08 |  |
| 11. | S/R of accessories of control panel boards of P/Sets Feeder Pillars i/c repairs & painting of various parks pertaining to Hort. Divn. No. 3. | 154440/- 120180/- | 35/EE/D2 2007-08 | M/s. H.S. Engg. Works | 06/11/06 05/11/07 |  |

As on 01/08/2007

3.	Projects heldup due to Court Cases :		NIL

Respective Court with Case No. 		:

Date of Next hearing 				:	N.A. in view of above.

4.	Detail of Deposit works

a)	In hand 				:	-------- NIL ---------

b)	Under approval 			:	-------- NIL---------

5.	Details of deviation in works

a)	Undertaken 				:	-------- NIL---------

b)	Proposed (in Principal approval	:	-------- NIL---------

6.	Restricted Call of Tenders 		:	-------- NIL---------

7.	Rescinded Works 			:

As on 01/08/2007

| S. No. | Name of Scheme | Estt./Tender Cost | Agreement No. | Agency | Date of Start Time of Comp. (Period) | Supplementary Agreement if Drawn | Physical ____% of Allotment | Present Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2693/2714 EWS & 358/376 L.I.G. Du’s in Pkt. 3, Bindapur. |  |  |  |  |  |  |  |
| (i) | 220 EWS + 20 L.I.G. Block B 3, Pkt. 3, Bindapur. | 430340/- | 56/EE/ED-2 2004-05 | M/s. Metro Elect. Co. | 03/04/05 12 Months | N/A | 50% | Under Allotment |
| (ii) | 202 EWS + 24 L.I.G. Block B 3, Pkt. 3, Bindapur. | 400015/- | 57/EE/ED-2 2004-05 | M/s. Metro Elect. Co. | 03/04/05 12 Months | N/A | 40% | Under Allotment |
| 2. | C/o 208 L.I.G. at Pkt. GH 3 in G-17, Paschim Vihar. | 908524/- 1820136/- | 44/EE/ED-4 2006-07 | M/s. Metro Elect. Co. | 26/11/06 9 Months | N/A | 70% | Under Allotment |

8.	      Court Case

Status Reports of Court Cases

As on 01/08/2007

| S. No. | File No. | Case / Suit Name of Court | Name of the court | Title of case | Name of Panel | Status of case | Date of Previous hearing | Date of hearing | Date of entrusted of Panel Lawer |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 4(56)07/DFII/legal | 519/07 | Consumer Disputes Redressed Forum II, Udog Sadan, C-22, 23 Ist ‘X’ Institutional Area Delhi -6 | Lalit Kapur V/S DDA (Party – I) | Sh. Neeraj Aggrawal | Lack intra Structures and basic amenities (Electrification at Plotted Pkt., Sec. – 13 Dwarka) | Nil | 13/09/07 | 21/05/07 |
| 2. | F.9(56)98/TC/Legal | ID/711/98 | Labour Court Karkarduma | Sh. Salekh Chand V/s DDA | Sh. Sanjay Sharma | Appeal against transfer to MCD | 22.5.07 | 21/08/07 | 15/01/.04 |
| 3. | F.2(1048)94/HC/Legal | 294/94 | Appeal stay from High Court | DDA V/s Satbir Singh | Sh. Arun Birbal | Appeal filed in High Court against judgement of ADJ. dt. On stay of transfer to MCD | Regular Hearing | Regular Hearing |  |

9.	Fire Fighting Equipments – Installation

As on 01/08/2007

| S. No. | Location | Wed Riser | Sprinkler | Fire Alarm | P/A System | Fire Extinguisher |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | 198 M.I.G., Pkt. 8, Sector – 12, Dwarka 1 No. | Yes | - | Yes | Yes | Yes |
| 2. | Distt. Centre, Janakpuri. 5 Nos. |  |  |  |  |  |
|  | Plot No. l | Yes | Yes | Yes | Yes | Yes |
|  | Plot No. 2 | Yes | Yes | Yes | Yes | Yes |
|  | Plot No. 5 | Yes | Yes | Yes | Yes | Yes |
|  | Plot No. 5A | Yes | Yes | Yes | Yes | Yes |
|  | Plot No. 7A | Yes | Yes |  |  |  |