LIST OF ACTIVITIES

| 1. | Details of Pending Final Bills & non-ref. of Security Deposits. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name of Work |  |  |  | Agencies |  |  |  |  |  | Agmt. No. |  |  |  |  |  | Esst. Cost. Tender Cost |  |  | Stipulated |  |  |  |  |  | Remarks |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | D.O.S. D.O.C. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (i) |  | D/o Yamuna River Front (West Bank) along Vijay Ghat (Pushta) S.H. : C/o Water body at Yamuna Pushta |  | M/s Amar Constn. Co. |  |  |  |  |  | 76/EE/ND-I/DDA/ 04-05 |  |  |  |  |  | Rs.60,36,559/- Rs.16,49,051/- |  |  | 07.03.2005 06.07.2005 |  |  |  |  |  | Due to non submission of case by the earlier staff. |  |  |  |  |  |  |  |  |
| (ii) |  | --DO— S.H. : C/o root-zone channel in Phase-I at Yamuna Pushta. |  | M/s Birender Constn. Co. |  |  |  |  |  | 36/EE/ND-1/DDA/04-05 |  |  |  |  |  | Rs.7,68,600/- Rs.2,33,520/- |  |  | 31.10.04 30.11.04 |  |  |  |  |  | --do-- |  |  |  |  |  |  |  |  |
| (iii) |  | All due securities are being refunded on the request of respective Agencies. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. |  | Present status of works |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| S. No |  | Name of work |  |  |  | ### Estt. Cost Tendered Cost |  |  |  |  |  | D.O.S. D.O.C. |  |  |  |  | Progress up to previus month |  |  | ## Progress during this month |  |  |  |  |  | Up to date progress |  |  |  |  | Remarks |  |  |
| (i) |  | D/O Green belt block B to I Ashok Vihar ph-1 SH: P/L Unfiltered water supply line in front of block B to E Agency: Rajinder Singh |  |  |  | Rs.6,30,584/- Rs.10,60,907/- |  |  |  |  |  | 27.04.07 26.06.07 |  |  |  |  | 65% |  |  | 35% |  |  |  |  |  | 100% |  |  |  |  | Completed D.O.C. 10.07.2007 |  |  |
| (ii) |  | D/O Green Belt along block B to I AshokVihar, Phase- 1 SH: C/O 2Nos. pump Agency: M/S Robin Const. Co. |  |  |  | Rs. 1,27,471/- Rs. 1,38,885/- |  |  |  |  |  | 30.01.07 30.03.07 |  |  |  |  | 80% |  |  | 20% |  |  |  |  |  | 100% |  |  |  |  | Completed D.O.C. 30.05.2007 |  |  |
| (iii) |  | M/O Park/plantation of Hort. Wing under North Zone SH: Repairing of bondary wall at Khoje Wala Bagh park, Ashok vihar Ph.-1 Agency : Bajrang Engineering |  |  |  | Rs.2,80,,534/- Rs.3,74,122/- |  |  |  |  |  | 26.03.07 25.05.07 |  |  |  |  | 80% |  |  | 20% |  |  |  |  |  | 100% |  |  |  |  | Completed D.O.C. 12.06.2007 |  |  |
| (iv) |  | D/O Janak Wala Bagh at Bharat Nagar , Ashok Vihar Ph.-IV SH: C/O Parking area in Ph.-I Agency : Sh. Kundan Lal |  |  |  | Rs.6,91,001/- Rs.7,16,164/- |  |  |  |  |  | 15.07.07 14.09.07 |  |  |  |  | - |  |  | - |  |  |  |  |  | - |  |  |  |  | Work started on 18.07.07 |  |  |
| (v) |  | D/O Janak wala Bagh at Bharat Nagar Ashok Vihar Ph.-IV SH: C/O Red bajri path Agency : Sh. Yash Pal Singh |  |  |  | Rs.5,24,268/- Rs.33,54,574/- |  |  |  |  |  | 22.07.07 21.09.07 |  |  |  |  | - |  |  | - |  |  |  |  |  | - |  |  |  |  | Work started on 18.07.07 |  |  |
| (vi) |  | M/O Park/plantation of Hort. Wing under North Zone SH: Rpairing of burnt room of A/C branch & sub division office of Hort. Division –II Rama Market Pitampura Agency: R. K. Rodhiya |  |  |  | Rs.2,37,419.00 Rs.2,40,619.00 |  |  |  |  |  | 10.05.07 09.07.07 |  |  |  |  | 10% |  |  | 90% |  |  |  |  |  | 100% |  |  |  |  | Completed D.O.C. 02.07.07 |  |  |
| (vii) |  | M/O Park/plantation of Hort. Wing under North Zone SH:Improvement of existing boundary wall in Gonal Green Park, Sarswati Vihar Agency : R. K. Rodhiya |  |  |  | Rs. 1,90,670/- Rs.1,68,197/- |  |  |  |  |  | 19.07.07 18.09.07 |  |  |  |  | - |  |  | - |  |  |  |  |  | - |  |  |  |  | Work started on 19.07.07 |  |  |
| (viii) |  | M/O Park/plantation of Hort. Wing under North Zone SH: Raising of existing grill at Harsh Vihar park Pitampura Agency : R. K. Rodhiya |  |  |  | Rs. 1,98,745/- Rs.2,35,138/- |  |  |  |  |  | 19.07.07 03.09.07 |  |  |  |  | - |  |  | - |  |  |  |  |  | - |  |  |  |  | Work started on 19.07.07 |  |  |
| (ix) |  | M/O Park/plantation of Hort. Wing under North Zone SH: Repair of boundary of wall in M. D. park Lawrence Road Agency: S.V. Const. |  |  |  | Rs.1,35,051/- Rs.1,74,691/- |  |  |  |  |  | 30.03.07 29.05.07 |  |  |  |  | 30% |  |  | - |  |  |  |  |  | 30% |  |  |  |  |  |  |  |
| (x) |  | M/O Park/plantation of Hort. Wing under North Zone SH: Repair of boundary wall and scatting ring Of distt. Park Pitampura Agecy: Pankaj Chhatirya |  |  |  | Rs.1,62,436/- Rs.1,31.174/- |  |  |  |  |  | 08.05.07 07.07.07 |  |  |  |  | 85% |  |  | 15% |  |  |  |  |  | 100% |  |  |  |  | Completed D.O.C..06.07.07 |  |  |
| (xi) |  | M/O Park/plantation of Hort. Wing under North Zone SH: Repair and restoration of boundary wall in Nepal Wala Bagh. Agency: N.K. Enterprises |  |  |  | Rs.2,55,941/- Rs.2,28,588/- |  |  |  |  |  | 14.05.07 13.07.07 |  |  |  |  | 85% |  |  | 15% |  |  |  |  |  | 100% |  |  |  |  | Completed D.O.C..10.07.07 |  |  |
| (xii) |  | M/O Park/plantation of Hort. Wing under North Zone SH: Improvement of foot path in Maharishi Daya Nand park at Lawrence road Agency : N.K. Enterprices |  |  |  | Rs.4,10,040/- Rs.2,72,981/- |  |  |  |  |  | 22.07.07 21.09.07 |  |  |  |  | - |  |  | - |  |  |  |  |  | - |  |  |  |  | Work yet to be start |  |  |
| (xiii) |  | M/O Park/plantation of Hort. Wing under North Zone SH: Repair of path and water supply line of Distt. Park Pitampura Agency : N.K. Enterprices |  |  |  | Rs.2,70,.594/- Rs. 1,86,433/- |  |  |  |  |  | 22.07.07 21.09.07 |  |  |  |  | - |  |  | - |  |  |  |  |  | - |  |  |  |  | Work yet to be start |  |  |
| (xiv) |  | M/O Park/plantation of Hort. Wing under North Zone SH: Improvement of foot path in Maharishi Daya Nand park at Lawrence road Agency : N.K. Enterprices |  |  |  | Rs.4,10,040/- Rs.2,72,981/- |  |  |  |  |  | 22.07.07 21.09.07 |  |  |  |  | - |  |  | - |  |  |  |  |  | - |  |  |  |  | Work yet to be start |  |  |
| (xv) |  | M/O Park/plantation of Hort. Wing under North Zone SH: Maintaince in R/O Sweeping, Scavanging, Cleaning of 4Nos. toilet and fountain area in distt. Park Pitampura Agency: M/S Venus Associates |  |  |  | Rs.44,4,36/- Rs.23,7,60/- |  |  |  |  |  | 24.03.07 23.09.07 |  |  |  |  | 50% |  |  | 15% |  |  |  |  |  | 65% |  |  |  |  |  |  |  |
| (xvi) |  | M/O Park/plantation of Hort. Wing under North Zone SH:Repair of boundary wall in parks near road no.42,Pitampura Agency:M/S N.K. Enterprises |  |  |  | Rs.492532/- Rs.3.15279/- |  |  |  |  |  | 26.04.07 25.06.07 |  |  |  |  | 100% |  |  | - |  |  |  |  |  | 100% |  |  |  |  | Completed |  |  |
| (xvii) |  | D/O Land Biodiversity park at Jharoda Mazra &Wazirabad SH: Cleaning & Sweeping of Nature Interpellation Center, path & parking in visitors area Agency: M/S Harender singh |  |  |  | Rs.82,392.00 Rs.52,800.00 |  |  |  |  |  | 18.07.07 17.07.08 |  |  |  |  | - |  |  | - |  |  |  |  |  | - |  |  |  |  | Work started on 18.07.07 |  |  |
| (xviii) |  | D/O Land Biodiversity park at Jharoda Mazra &Wazirabad SH: Strengthening of approach road from Junction to Yamuna Biodiversity Park Agency: M/S A.S.Builder |  |  |  | Rs.35.04, 89/- Rs.,41,75,570/- |  |  |  |  |  | 07.09.06 06.01.07 |  |  |  |  | 5% |  |  | 65% |  |  |  |  |  | 70% |  |  |  |  |  |  |  |
| (xix) |  | D/O land under North Zone SH: C/O boundary wall of park between Sanik Vihar and Shakti Vihar Agency: Robin const. co. |  |  |  | Rs. 9,16,334/- Rs. 12,60,267/- |  |  |  |  |  | 26.04.07 25.06.07 |  |  |  |  | 10% |  |  | 25 |  |  |  |  |  | 35% |  |  |  |  |  |  |  |
| 3. |  | Projects held up due to Court Case -- Respective Court with Case No. -- Date of Next Hearing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Nil |  |  |  |  |  |  |  |  |  |
| 4. |  | Rain Water Harvesting -- Already Provided -- Proposed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Nil Nil |  |  |  |  |  |  |  |  |  |
| 5. |  | Water bodies -- identified, status & under encroachment. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | There are three numbers developed water body identified as water body No. 41(a), 42(a) and 34(a) |  |  |  |  |  |  |  |  |  |
| 6. |  | Details of Deposit Works : (a) in hand (b) Under approval - Status |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Nil |  |  |  |  |  |  |  |  |  |
| 7. |  | Details of deviation in works : (a) Undertaken (b) Proposed (In Principle Approval) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| S.No. |  | Name of work |  |  |  |  |  | Agency |  |  | Agg. No. |  |  |  |  |  | Tendered Amount |  |  |  |  | Total Work Done |  |  |  |  | Deviation |  |  |  |  | Remarks |  |
| (i) |  | Park and Plantation of Horti Wing under North Zone. S.H. : R/o Burnt Room A/c Branch and Sub-Division Horticulture Division, Rama Market, Pitampura |  |  |  |  |  | R.K. Rodhiya |  |  | 6/EE/ND1/ 2007-2008 |  |  |  |  |  | 2,40,619.00 |  |  |  |  | 2,80,956.00 |  |  |  |  | 16.76% |  |  |  |  | a) Deviation already passed in form of Extra Item Statement-I by the Competent Authority. b) Nil |  |
| (ii) |  | Fencing of vacant land under North Zone. S.H. : Removal / Disposal of building rubbish from koki wala Bagh to temple at Bharat Nagar Ashok Vihar, Phase-IV. |  |  |  |  |  | Ramesh Chillar |  |  | 53/EE/ND1/DDA/2006-2007 |  |  |  |  |  | 4,96,260.00 |  |  |  |  | 5,48,462.00 |  |  |  |  | (+) 10.52% |  |  |  |  | a) Deviation already passed by the Competent Authority. b) Nil |  |
| (iii) |  | M/o parks / plantation of Hort Wing under North Zone S.H. : Repairing of foot path & disposal of malba at N.H.8, Satyawati Colony, Ashok Vihar, Phase-IV |  |  |  |  |  | M/s Robin Constn. Co. |  |  | 55/EE/ND-I/DDA/2006-2007 |  |  |  |  |  | 1,09,000/- |  |  |  |  | 1,29,164/- |  |  |  |  | (+) 18.50% |  |  |  |  | a) Deviation already passed by the Competent Authority. b) Nil |  |
| (iv) |  | Fencing of DDA Land under North Zone S.H. : Repairing of B/Wall and providing missing grills on B/Wall at picnic Hut Ashok Vihar, Ph-III |  |  |  |  |  | M/s Anurag Brothers |  |  | 47/EE/DN1/DDA/2006-2007 |  |  |  |  |  | 1,50,843/- |  |  |  |  | 1,68,685/- |  |  |  |  | (+) 11.83% |  |  |  |  | a) Deviation already passed by the Competent Authority. b) Nil |  |
| (v) |  | M/o Parks / plantation of Hort. Wing under North Zone S.H. : Repair of Distt. Part at Multan Nagar. |  |  |  |  |  | Sh. Ramesh Kumar Rodhiya |  |  | 59/EE/ND1/DDA/2006-2007 |  |  |  |  |  | 1,96,143.00 |  |  |  |  | 2,44,688.00 |  |  |  |  | 24.75% |  |  |  |  | a) Deviation already passed by the Competent Authority. b) Nil |  |
| (vi) |  | M/o Parks / Plantation of Hort Wing under North Zone. S.H. : Repair in Parks near Parmarth Hospital, Pitampura, Delhi |  |  |  |  |  | M/s Vats Constn. Co. |  |  | 01/EE/ND1/DDA/07-08 |  |  |  |  |  | 2,22,502.00 |  |  |  |  | 2,47,532.00 |  |  |  |  | 11.24% |  |  |  |  | a) Deviation already passed by the Competent Authority. b) Nil |  |
| 8. |  |  | Restricted Call of tenders |  |  |  |  |  | D/o Land for Bio-diversity park at Jharoda Mazra and Wazirabad S.H. : Arrangement of Private Security along Green House Office Building, Interpretation Center and in the area. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9. |  |  | Rescinded Works. |  |  |  |  |  | Nil |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10. |  |  | Arbitration & related Court Cases |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a) |  |  | Arbitration |  |  |  |  |  | Nil |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| b) |  |  | Court Cases |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| S.No |  |  | Description of Item |  |  |  | Agency |  |  |  |  |  |  | Name of Court Case No. |  |  |  |  |  |  |  |  | Name of P/L |  |  |  |  |  |  | Next date of Hearing |  |  |  |
| (i) |  |  | C/o 560 MIG DU’s at Pkt. (P) Pitampura S.H. : C/o 192 MIG DU’s at Pitampura |  |  |  | M/s Prakash Sharma |  |  |  |  |  |  | Supreme Court SLP (C) 2872/01 |  |  |  |  |  |  |  |  | Mrs. Kum Kum Sen. |  |  |  |  |  |  | Pending for want of irregular hearing |  |  |  |
| (ii) |  |  | C/o 720 LIG DU’s at Pitampura Pkt. W(P) SH. : C/o 396 LIG DU’s at Pitamprua Pkg. W(P) i/c Internal services. |  |  |  | M/s Sudhir Brothers |  |  |  |  |  |  | High Court OMP. 93/88 |  |  |  |  |  |  |  |  | Mrs. A. Salwan |  |  |  |  |  |  | Pending for want of hearing w.e.f. 27.07.2006 |  |  |  |
| (iii) |  |  | C/o 330 LIG Incremental houses i/c internal water supply sanitary installation & internal development work in sector B-IV Pkt. 6 Gr.1 at Narela. |  |  |  | M/s Nav Bharat Const. Co. |  |  |  |  |  |  | High Court OMP 285/06 |  |  |  |  |  |  |  |  | Sh. Bhupesh Narula |  |  |  |  |  |  | 14.08.2007 |  |  |  |
| (iv) |  |  | C/o 770/324 LIG DU’s at Pitampura Pkt. (W) (P) |  |  |  | M/s Verma Const. Co. |  |  |  |  |  |  | High Court OS-765/06 |  |  |  |  |  |  |  |  | Sh. Bhupesh Narula |  |  |  |  |  |  | 23.07.2007 |  |  |  |
| (v) |  |  | C/o MIG / LIG Shop & Services 256 Hact. Land at Sarai Khalil SG : C/o Road (Balance work) |  |  |  | M/s Ajay Verma |  |  |  |  |  |  | Tis Hazari EY/123/06 |  |  |  |  |  |  |  |  | S.L.O. (T.C.) |  |  |  |  |  |  | 07.09.2007 |  |  |  |
| (vi) |  |  | C/o 64 Three B/R 64 Two B/R & 96 Scooter Garage under SFS at Pitamprua |  |  |  | M/s Sudhir Brothers |  |  |  |  |  |  | Tis Hazari 112/03 |  |  |  |  |  |  |  |  | Mrs. Beena Sharma |  |  |  |  |  |  | 17.08.2007 |  |  |  |
| (vii) |  |  | M/o Parks / Plantation Hort. Wing under North Zone SH. : Sinking of tubewell & P/F unfiltered water line behind of Kirpal Bagh (Joginder Wala Bagh) Gujaran Wala Town Phase-III |  |  |  | Sh. S.D. Falwaria |  |  |  |  |  |  | Tis Hazari 87/2005 |  |  |  |  |  |  |  |  | Mrs. Shushma Sharma |  |  |  |  |  |  | 21.07.2007 |  |  |  |
| (viii) |  |  | D/o green belt in front of Bl. E to I in Ashok Vihar Phase-I SH. : C/o Cement Concrete tiles and moorum path in front of bl. E to I. |  |  |  | M/s Durga Const. Co. |  |  |  |  |  |  | Tis Hazari 216/04 |  |  |  |  |  |  |  |  | Sh. K.D. Sharma |  |  |  |  |  |  | 23.07.2007 |  |  |  |
| 11. |  |  | Details of Q.C. Lab. Tests, procedures |  |  |  |  |  | N.A. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12. |  |  | Fire fighting Equipments : Installed (Nos.) with Location |  |  |  |  |  | Not installed as yet |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13. |  |  | List of Soil Testing Laboratories |  |  |  |  |  | Are issued by E.M. Office |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14. |  |  | List of Approved Structural Consultants |  |  |  |  |  | Does not pertain to this office |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15. |  |  | Technical Circulars |  |  |  |  |  | Are issued by V.C., E.M., C.E. (Q.C.) and Vigilance Department |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 16. |  |  | Q.C. Circulars |  |  |  |  |  | Are issued by QAC, DDA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17. |  |  | List of Contractors, A, B, C, D categories |  |  |  |  |  | Pertains to CRB/DDA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 18. |  |  | RIS/ EIS/ EOT Cases & Completion Certificate |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| S.No |  |  | Name of Work |  |  | Agency |  |  |  |  | Agreement No. |  |  |  | EIS |  |  | RIS |  |  |  |  | SIS |  |  |  |  | Amount |  |  |  |  | EOT |
| (i) |  |  | M/o Parks / Plantation of Hort. Wing under North Zone. S.H. : R/o Burnt room A/c branch and Sub-Div.-II Rama Market, Pitampura |  |  | R.K. Rodhiya |  |  |  |  | 6/EE/ND1/ 2007-08 |  |  |  | EIS No.1 |  |  | -- |  |  |  |  | -- |  |  |  |  | 40337/- |  |  |  |  | EOT not required |
| (ii) |  |  | Fencing of DDA land under North Zone S.H. : Repairing of B/wall and providing missing grills on B/Wall at Picnic Hut Ashok Vihar, Ph-III |  |  | M/s Anurag Brothers |  |  |  |  | 47/EE/ND1/ 2006-07 |  |  |  | EIS No.1 |  |  | -- -- |  |  |  |  | I -- |  |  |  |  | 17032/- 3145/- |  |  |  |  | Not required |
| (iii) |  |  | D/o Yamuna River Front (West Bank) along Vijay Ghat (Pushta) S.H. : C/o Water body at Yamuna Pushta |  |  | M/s Amar Constn. Co. |  |  |  |  | 76/EE/ND-I/DDA/ 04-05 |  |  |  | -- |  |  | -- |  |  |  |  | -- |  |  |  |  | -- |  |  |  |  | Remarks C.C. to be recorded |
| (iv) |  |  | --DO— S.H. : C/o root-zone channel in Phase-I at Yamuna Pushta. |  |  | M/s Birender Constn. Co. |  |  |  |  | 36/EE/ND-1/DDA/04-05 |  |  |  | -- |  |  | -- |  |  |  |  | -- |  |  |  |  | -- |  |  |  |  | Remarks C.C. sent to competent authority for counter signed |
| (v) |  |  | M/O Parks & Plantation of Hort. Wing under North Zone. S.H. : Repair of Distt. Park at Multan Nagar. |  |  | Sh. Ramesh Kumar Rodhiya |  |  |  |  | 59/EE/ND1/DDA/2006-2007 |  |  |  | EIS No. I |  |  | -- |  |  |  |  | -- |  |  |  |  | 4131/- |  |  |  |  | E.O.T. Not required |
| (vi) |  |  | M/o Parks Plantation of Hort Wing under North Zone S.H. : Repair in Parks near Parmarth Hospital Pitampura |  |  | M/s Vats Cons. Comp. |  |  |  |  | 1/EE/ND1/DDA/2007-2008 |  |  |  | EIS No.1 |  |  | -- |  |  |  |  | -- |  |  |  |  | 8462/- |  |  |  |  | --do-- |
| (vii) |  |  | M/o Parks & Planatation & Hort Wing under North Zone S.H. : Repair and Boundary Wall in Parks near Road No.42 Pitampura |  |  | M/s N.K. Enterprises |  |  |  |  | 4/EE/ND1/DDA/2007-2008 |  |  |  | EIS No.1 |  |  | -- |  |  |  |  | -- |  |  |  |  | 14000/- |  |  |  |  | --do-- |
| (viii) |  |  | M/o Parks and Plantation Hort Wing under North Zone. S.H. : Repair & Restoration of Boundary Wall in Nepal Wala Bagh Lawrence Road |  |  | M/s N.K. Enterprises |  |  |  |  | 4/EE/ND1/ DDA/ 2007-2008 |  |  |  | EIS No.1 EIS No.2 |  |  | -- -- |  |  |  |  | -- -- |  |  |  |  | 14000/- 30451/- |  |  |  |  | -do-- |
| 19. |  |  | List of approved rates of SE (P) |  |  |  |  |  | Are issued by Chairman Market Rate Approval Committee / Concerned SE (P) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 20. |  |  | Areas where services are handed over to MCD / DJB & Deficiency charges |  |  |  |  |  | N.A. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 21. |  |  | List of vacant flats / Shops / Keosk / Commercial / Residential Plots on the date of completion / development. |  |  |  |  |  | N.A. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 22. |  |  | Jurisdiction of C.E. / Map. EE wise |  |  |  |  |  | Asstt. Engineer-I - D/o land for Bio-diversity Park at Jharoda Mazra Wazirabad Phase-I & II - D/o Park between Sainik Vihar AND Shakti Vihar - D/o Park at Sandesh Vihar and Shakti Vihar - Ashok Vihar Phase-II - Khojjay Wala Park - Children Play Area - 21 Bigha Park - Chandi Wala Park - NHP at Bada Kuan - Ashok Vihar Phase-III - Khimmen Singh Park - Picnic Hut with Park - NHP at Satyawati Colony Asstt. Engineer-II - Sanjay Van Park Pitampura - Distt. Park Harsh Vihar Pitampura - Distt. Park Saraswati Vihar, Pitampura - Lok Vihar, Pitampura - Kohat Enclave, Pitampura - Sanjay Park, Pitampura - Western Enclave Park, Pitampura - Suvidha Kunj Park, Pitampura - Tarun Enclave, Pitampura - Brij Vihar, Pitampura - Anand Vihar, Pitampura - Deepali Chowk, Pitampura - Chanderlok Pitampura - Orchid and Shakurpur - Rajdhani Enclave Pitampura Asstt. Engineer-III - Ashok Vihar Phase-I - Green Belt along Block B to I - Lekh Ram Park - Ashok Vihar Phase-IV - Ashoka Garden - Zonal Green - Bharat Nagar (a) Janak Wala Bagh - Shastri Nagar - 56 Bigha Park - Shastri Nagar Park - Gulabi Bagh - District Park - Sindhora Kalan Park - Faiz Road Park - Idgah Park Asstt. Engineer-IV - Distt. Park Pitampura - NHP at Block H(U) Pitampura - Distt. Park Double Tank Pitampura - NHP at Lala Wala Bagh at Pitampura - ND Park Pitampura - Distt. Park Multan Nagar (Sehdev Singh Park) Punjabi Bagh - NHP Near Parmarth Hospital Pitampura - NHP at Near NH 42 Pitampura - Mazdoor Wala Park at Lawrence Road - Rose Garden Park at Lawrence Road - Nepal Wala Bagh at Lawrence Road - Pahari Wala Bagh at Lawrence Road - MD Park at Lawrence Road - NHP at Block T (P) Pitampura - NHP at Block T(P) & S(P) Pitampura - Aziz Bux Wala Bagh at Pitampura - NHP at Block R(P) Pitampura |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 23. |  |  | Details of land handed over to Engineering Wing for development |  |  |  |  |  | 157 Acre for D/o Land Bio-Diversity Park at Jharoda Mazra PH-I is in progress and 300 Acre land for Bio-diversity Park at Jharoda Mazra Wazirabad Ph-II has been taken over by Engineering Wing. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 24. |  |  | Sanctioned Strength / In place / vacancy position of Regular Staff |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| S.No |  |  | Designation |  | Sanctioned Strength |  |  |  |  |  |  |  | Men in Position |  |  |  |  |  |  |  | Shortfall |  |  |  |  |  |  |  | Excess |  |  |  |  |
| 1. |  |  | E.E. © |  | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |  | -- |  |  |  |  |
| 2. |  |  | A.E. © |  | 5 |  |  |  |  |  |  |  | 4 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  | -- |  |  |  |  |
| 3. |  |  | A.A.O. |  | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |  | -- |  |  |  |  |
| 4. |  |  | Head Clerk |  | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |  | -- |  |  |  |  |
| 5. |  |  | Steno |  | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |  | -- |  |  |  |  |
| 6. |  |  | J.E. (C) |  | 12+1 |  |  |  |  |  |  |  | 13+1 |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |  | 1 |  |  |  |  |
| 7. |  |  | D/Man |  | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |  | -- |  |  |  |  |
| 8. |  |  | U.D.C. |  | 4 |  |  |  |  |  |  |  | 4 |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |  | -- |  |  |  |  |
| 9. |  |  | L.D.C. |  | 6 |  |  |  |  |  |  |  | 3 |  |  |  |  |  |  |  | 3 |  |  |  |  |  |  |  | -- |  |  |  |  |
| 10. |  |  | Daftry |  | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |  | -- |  |  |  |  |
| 11. |  |  | Peon |  | 4 |  |  |  |  |  |  |  | 4 |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |  | -- |  |  |  |  |
| 12. |  |  | S.C.D. |  | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |  | -- |  |  |  |  |

EXECUTIVE ENGINEER

ND-1, DDA