DELHI DEVELOPMENT AUTHORITY

ELECTRICAL DIVISION NO. – 6

List of works more than one lakh

REPORT AS ON 	30-11-2007

| S.No. | Name of Work | Estt. Cost (Fig. in Lac) | Tendered Cost | Agmt. No. | Agency | Dt. of start as per Agmt. | Dt. of Compl. as per Agmt. | Physical progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | D/O 92 Hact. of land at Vasant Kunj Ph.II West of JNU (SH :- S/I of clear water, Booster pumping station at Command Tank Vasant Kunj Ph. II. | 42.76 | 49.25 | 90/EE/El.D-6/ 06-07 | M/S N.K. Engg. Works. | 9.3.07 | 8.9.08 | 50% |
| 2. | 860/830 DU’s (2 rooms with lounge) on the East of Sect. D-6 i/c Int. Dev. work Civil & Elect. Vasant Kunj. |  |  |  |  |  |  |  |
| i) | C/O 290 DU’s in Gr. I | 25.94 | 40.76 | 76/EE/El.D-6/ 06-07 | M/S A.K. Gupta & Co. | 19.5.06 | 18.5.08 | 35% |
| ii) | C/O 270 DU’s in Gr. II | 23.71 | 35.36 | 77/EE/El.D-6/ 06-07 | M/S Bhupinder Kumar | 19.5.06 | 18.5.08 | 50% |
| iii) | C/O 270 DU’s in Gr. III | 23.71 | 36.57 | 81/EE/El.D-6/ 06-07 | M/S Surinder Kumar | 19.5.06 | 18.5.08 | 20% |
| 3. | D/O 92 Hact. land at Vasant Kunj Ph. II West of JNU (SH :- IEI of Pumping Stn. and S/Stn. Bldg. at Command Tank in Institutaional Area. | 2.21 | 2.43 | 83/EE/ED-6/ 06-07 | M/S Delight Trading Co. | 3.1.07 | 30.4.07 | 50% |
| 4. | M/O Scheme under Nazul A/C-II SWZ SH :- Operation and Maint. of Sub.P/Set fountain 11KV/440V package type S/Stn. Picnic Hut path light at Deer park and path park Hauz Khas. | 5.19 | 4.01 | 63/EE/ED-6/ 06-07 | M/S Gurnam Bros. | 23.11.07 | 22.11.08 | 100% |
| 5. | M/O Scheme under N.A.II SWZ (SH :- Operation and maintenance of Sub. P/Set park and pathway lights at NHP Sect. 12 R.K. Puram and Nanakpura nursery Dhaula Kua Sect. 5&6 Vasant Kunj, Catcus garden V. Kunj Vasant Vatika V. Kunj | 2.06 | 1.49 | 79/EE/ED-6/ 07-08 | M/S Gurnam Bros. | 6.5.07 | 5.5.08 | 55% |
| 6. | D/o Aravali Biodiversity Park at Vasant Kunj, Phase-II, (Main and operation of Camp Office and Electrical Installation and Pump set at Bio diversity Park, Vasant Kunj. Ph-II. | 1.83 | 1.79 | 61/EE/ED6/DDA/ 7-8 | K.S. Engineering works | 29.10.06 | 28.10.07 | 100% |
| 7. | M/s. Scheme under N/A-II, SWZ (SH operation and maint of sub pumpset, park light and fountain at Rose Garden, Hauz Khas. | 1.96 | 1.94 | 49/EE/ED-6/DDA/06-07 | M/s. Gurnam Bros. | 26.09.06 | 25.09.07 | 100% |
| 8. | M/o Scheme under Nazul a/c –II (SWZ) (Repairing and Rewinding of sub. pumpset at various site under Horticulture div-IV | 3.72 | 3.87 | 17/EE/ED6/DDA/ 07-08 | M/s. Pump Engineering & Associate. | 14.08.07 | 13.08.08 | 20% |
| 9. | Scheme under N/A II SWZ (SH Operation and mountenace of sub Pumpset Park light and path way light at Distt park Vasant Vihar) | 1.86 | 1.15 | 24/EE/ED6/DDA/ 07-08 | M/s Gurnam Bros. | 28.10.07 | 27.10.08 | 10% |
| 10. | M/o Scheme under N/A II SWZ (SH Operation and Maint of Sub Pumpset Park Light Path Way Light at NHP Sec- A Pat – A, Pocket B % C Simirti Van Vasant Kunj) | 1.80 | 1.12 | 25/EE/ED6/DDA/ 07-08 | M/s Gurnam Bros | 28.10.07 | 27.10.08 | 10% |
| 11. | C/o 160 HIG Cat II Houses in LIC Pocket Sec – B Pkt – 2 Vasant Kunj C- SH IEI in 64 Houses in GR – I | 24.13 | 28.23 | 26/EE/ED6/DDA/ 07-08 | M/s Goel Electrical | 6.11.07 | 5.5.2010 |  |
| 12. | C/o 160 HIG Cat II Houses in LIC Pocket Sec – B Pkt – 2 Vasant Kunj C- SH IEI in 64 Houses in GR – II | 21.45 | 25.09 | 27/EE/ED6/DDA/ 07-08 | M/s Goel Electrical | 6-11-07 | 5.5.2010 |  |
| 13. | M/o Scheme under N/A II SWZ Operation and mantenace of sub pumpset, park light, path way light at picnic but mehrauli New Delhi | 1,78, | 1,28 | 28/EE/ED6/DDA/ 07-08 | M/s Gurnam Bros | 28.11.07 | 27.11.08 |  |
| 14. | M/o Scheme under nauzal A/C II SWZ Operation and maint os sub pumpset Park light and path way light at Janali Kamali | 1, 32. | 0.94 | 29/EE/ED6/DDA/ 07-08 | M/s Gurnam Bros | 28.11.07 | 27.11.08 |  |
| 15. | M/o Scheme undr nauzal A/c II SWZ Operation and maint of sub Pumpset Park light and path way light and founction at Rose Garden Hauz Khas | 1,21 | 0.80 | 30/EE/ED6/DDA/ 07-08 | M/s Gurnam Bros | 28.11.07 | 27.11.08 |  |
| 16. | Seheme under nauzal A/C II SWZ (SH Operation and mount of Sub Pumpset Park light and path way light at SDA Park Hauz Khas) | 1,24 | 0.80 | 31/EE/ED6/DDA/ 07-08 | M/s Gurnam Bros | 28.11.07 | 27.11.08 |  |

(R.P.S. LUTHRA)

EXECUTIVE ENGINEER (E) El.D.-6/DDA