LIST OF ACTIVITIES

NORTH ZONE DDA

# CIRCLE :- CIVIL CIRCLE –7								DIVISION : NORTHERN DIVISION  - 1

| 1. | Details of Pending Final Bills & non-ref. of Security Deposits. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name of Work |  |  |  | Agencies |  |  |  |  |  | Agmt. No. |  |  |  |  |  | Esst. Cost. Tender Cost |  |  | Stipulated |  |  |  |  |  | Remarks |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | D.O.S. D.O.C. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (i) |  | D/o Yamuna River Front (West Bank) along Vijay Ghat (Pushta) S.H. : C/o Water body at Yamuna Pushta |  | M/s Amar Constn. Co. |  |  |  |  |  | 76/EE/ND-I/DDA/ 04-05 |  |  |  |  |  | Rs.60,36,559/- Rs.16,49,051/- |  |  | 07.03.2005 06.07.2005 |  |  |  |  |  | Due to non submission of case by the earlier staff. |  |  |  |  |  |  |  |  |
| (ii) |  | --DO— S.H. : C/o root-zone channel in Phase-I at Yamuna Pushta. |  | M/s Birender Constn. Co. |  |  |  |  |  | 36/EE/ND-1/DDA/04-05 |  |  |  |  |  | Rs.7,68,600/- Rs.2,33,520/- |  |  | 31.10.04 30.11.04 |  |  |  |  |  | --do-- |  |  |  |  |  |  |  |  |
| (iii) |  | All due securities are being refunded on the request of respective Agencies. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. |  | Present status of works |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| S. No |  | Name of work |  |  |  | ### Estt. Cost Tendered Cost |  |  |  |  |  | D.O.S. D.O.C. |  |  |  |  | Progress up to previus month |  |  | ## Progress during this month |  |  |  |  |  | Up to date progress |  |  |  |  | Remarks |  |  |
| (i) |  | D/O Land Biodiversity park at Jharoda Mazra &Wazirabad SH: Cleaning & Sweeping of Nature Interpellation Center, path & parking in visitors area Agency: M/S Harender singh |  |  |  | Rs.82,392.00 Rs.52,800.00 |  |  |  |  |  | 18.07.07 17.07.08 |  |  |  |  | 25% |  |  | 15% |  |  |  |  |  | 40% |  |  |  |  | Work started on 18.07.07 |  |  |
| (ii) |  | D/O land under North Zone SH: C/O boundary wall of park between Sanik Vihar and Shakti Vihar Agency: Robin const. Co. |  |  |  | Rs. 9,16,334/- Rs. 12,60,267/- |  |  |  |  |  | 26.04.07 25.06.07 |  |  |  |  | 80% |  |  | 20% |  |  |  |  |  | 100% |  |  |  |  |  |  |  |
| (iii) |  | D/o Land Bio-Diversity Park at Jharoda Majra and Wazirabad SH : Providing sitting arrangement by constructing RR Masonry wall at Amphi Theatro M/s Bajrang Engineering |  |  |  | Rs.2,05,796/- Rs.1,54,237/- |  |  |  |  |  | 29.07.07 11.09.07 |  |  |  |  | 20% |  |  | 60% |  |  |  |  |  | 80% |  |  |  |  |  |  |  |
| (iv) |  | D/o Land Bio-Diversity Park at Jharoda Majra and Wazirabad SH : C/o RCC Pipe drain M/s Bajrang Engineering |  |  |  | Rs. 1,75,738/- Rs. 1,63,034/- |  |  |  |  |  | 07.08.07 06.10.07 |  |  |  |  | - |  |  | 20% |  |  |  |  |  | 20% |  |  |  |  |  |  |  |
| (v) |  | D/o Park between Sainik Vihar & Shakti Vihar, Pitam Pura SH : C/o Footpath M/s B.S.Builder |  |  |  | Rs.16,99,040/- Rs. 11,06,324/- |  |  |  |  |  | 01.09.07 31.10.07 |  |  |  |  | - |  |  | - |  |  |  |  |  | - |  |  |  |  | Transfer to ND-11 |  |  |
| (vi) |  | D/o Park between Sainik Vihar & Shakti Vihar, Pitam Pura SH : C/o Soft Parking Sh. Yash Pal Singh |  |  |  | Rs.11,74,777/- Rs.11,20,494/- |  |  |  |  |  | 04.09.07 03.12.07 |  |  |  |  | - |  |  | - |  |  |  |  |  | - |  |  |  |  | Transfer to ND-11 |  |  |
| (vii) |  | M/o park / plantation of Hort. Wing under North Zone SH : Repair of Boundary Wall and painting of MS Grill in park Block S(P) and T(P) Pitam Pura Sh. R.K.Rodiya |  |  |  | Rs.1,66,358/- Rs.1,44,942/- |  |  |  |  |  | 25.09.07 08.11.07 |  |  |  |  | 20% |  |  | 80% |  |  |  |  |  | 100% |  |  |  |  | Completed 26-10-07 |  |  |
| (viii) |  | M/o park / plantation of Hort. Wing under North Zone SH : Improvement of Baradari and fountain pond at Picnic Hut Park (Ashok Vihar Ph.III) Sh. R.K.Rodiya |  |  |  | Rs. 1,72,474/- Rs.1,54,429/- |  |  |  |  |  | 28.09.07 27.11.07 |  |  |  |  | - |  |  | - |  |  |  |  |  | - |  |  |  |  | Transfer to ND-11 |  |  |
| (ix) |  | D/o District Park at Sandesh Vihar Pitam Pura, SH : Sinking of Tube-Well (5 Nos.) M/s Soni Tube-Well Works |  |  |  | Rs.6,18,919/- Rs. 9,04,710/- |  |  |  |  |  | 28.09.07 27.11.07 |  |  |  |  | - |  |  | - |  |  |  |  |  | - |  |  |  |  | Completed 22-10-07 |  |  |
| (x) |  | M/o park / plantation of Hort. Wing under North Zone SH : Repair of Footpath and Boundary Wall of District Park Double Tank Pitam Pura Sh. R.K.Rodiya |  |  |  | Rs.3,49,893/- Rs.3,41,984/- |  |  |  |  |  | 01.10.07 30.11.07 |  |  |  |  | 20%` |  |  | 80% |  |  |  |  |  | 100% |  |  |  |  | Completed 26-10-07 |  |  |
| (xi) |  | C/o 336 Multi Storeyed HIG Houses at Mukherjee Nagar, SH : C/o 96 Multistoreyed HIG houses i/c pile foundation and internal electrification All complete Group II M/s Winner Construction Co. |  |  |  | Rs.8,77,43,884/- Rs.13,59,71,180/- |  |  |  |  |  | 31.08.07 30.08.09 |  |  |  |  | - |  |  | - |  |  |  |  |  | - |  |  |  |  | Design mix approved by CE (NZ). Test piles being cast. |  |  |
| (xii) |  | D/o Land Bio-Diversity Park at Jharoda Majra and Wazirabad SH : Raising of Stone Masonary B/Wall with random rubber at top fixed with concertina coil in corridor of Ph-I and II M/S A.G. Constructions Co. |  |  |  | Rs.4,64,489/- Rs.4,29,927/- |  |  |  |  |  | 16.10.05 15.11.07 |  |  |  |  | - |  |  | 20% |  |  |  |  |  | 20% |  |  |  |  |  |  |  |
| (xiii) |  | D/o Land Bio-Diversity Park at Jharoda Majra and Wazirabad SH : R/O damaged & Sunk grass Pavement / Path on main trail near R.C.C. bridge. M/S Sharma Constructions Co. |  |  |  | Rs.6,36,446/- Rs.4,95,085/- |  |  |  |  |  | 05.11.07 18.01.08 |  |  |  |  | - |  |  | - |  |  |  |  |  | - |  |  |  |  | Work yet to be start |  |  |
| 3. |  | Projects held up due to Court Case -- Respective Court with Case No. -- Date of Next Hearing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Nil |  |  |  |  |  |  |  |  |  |
| 4. |  | Rain Water Harvesting -- Already Provided -- Proposed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Nil Nil |  |  |  |  |  |  |  |  |  |
| 5. |  | Water bodies -- identified, status & under encroachment. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | There are three numbers developed water body identified as water body No. 41(a), 42(a) and 34(a) |  |  |  |  |  |  |  |  |  |
| 6. |  | Details of Deposit Works : (a) in hand (b) Under approval - Status |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Nil |  |  |  |  |  |  |  |  |  |
| 7. |  | Details of deviation in works : (a) Undertaken (b) Proposed (In Principle Approval) Nil |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| S.No. |  | Name of work |  |  |  |  |  | Agency |  |  |  | Agg. No. |  |  |  |  | Tendered Amount |  |  |  |  | Total Work Done |  |  |  |  | Deviation |  |  |  |  | Remarks |  |
| 8. |  |  | Restricted Call of tenders |  |  |  |  |  | S.H.: Improvement of park by providing Tubewell in Mazdoor wala park at Lawrence Rd. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9. |  |  | Rescinded Works. |  |  |  |  |  | Nil |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10. |  |  | Arbitration & related Court Cases |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a) |  |  | Arbitration |  |  |  |  |  | Nil |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| b) |  |  | Court Cases |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| S.No |  |  | Description of Item |  |  |  | Agency |  |  |  |  |  |  | Name of Court Case No. |  |  |  |  |  |  |  |  | Name of P/L |  |  |  |  |  |  | Next date of Hearing |  |  |  |
| (i) |  |  | C/o 560 MIG DU’s at Pkt. (P) Pitampura S.H. : C/o 192 MIG DU’s at Pitampura |  |  |  | M/s Prakash Sharma |  |  |  |  |  |  | Supreme Court SLP (C) 2872/01 |  |  |  |  |  |  |  |  | Mrs. Kum Kum Sen. |  |  |  |  |  |  | Pending for want of irregular hearing |  |  |  |
| (ii) |  |  | C/o 720 LIG DU’s at Pitampura Pkt. W(P) SH. : C/o 396 LIG DU’s at Pitamprua Pkg. W(P) i/c Internal services. |  |  |  | M/s Sudhir Brothers |  |  |  |  |  |  | High Court OMP. 93/88 |  |  |  |  |  |  |  |  | Mrs. A. Salwan |  |  |  |  |  |  | Pending for want of hearing w.e.f. 27.07.2006 |  |  |  |
| (iii) |  |  | C/o 330 LIG Incremental houses i/c internal water supply sanitary installation & internal development work in sector B-IV Pkt. 6 Gr.1 at Narela. |  |  |  | M/s Nav Bharat Const. Co. |  |  |  |  |  |  | High Court OMP 285/06 |  |  |  |  |  |  |  |  | Sh. Bhupesh Narula |  |  |  |  |  |  | 15.02.2008 |  |  |  |
| (iv) |  |  | C/o 770/324 LIG DU’s at Pitampura Pkt. (W) (P) |  |  |  | M/s Verma Const. Co. |  |  |  |  |  |  | High Court OS-765/06 |  |  |  |  |  |  |  |  | Sh. Bhupesh Narula |  |  |  |  |  |  | 15.11..2007 |  |  |  |
| (v) |  |  | C/o MIG / LIG Shop & Services 256 Hact. Land at Sarai Khalil SG : C/o Road (Balance work) |  |  |  | M/s Ajay Verma |  |  |  |  |  |  | Tis Hazari EY/123/06 |  |  |  |  |  |  |  |  | S.L.O. (T.C.) |  |  |  |  |  |  | 02.11..2007 |  |  |  |
| (vi) |  |  | C/o 64 Three B/R 64 Two B/R & 96 Scooter Garage under SFS at Pitamprua |  |  |  | M/s Sudhir Brothers |  |  |  |  |  |  | Tis Hazari 112/03 |  |  |  |  |  |  |  |  | Mrs. Beena Sharma |  |  |  |  |  |  | 20.11.2007 |  |  |  |
| (vii) |  |  | M/o Parks / Plantation Hort. Wing under North Zone SH. : Sinking of tubewell & P/F unfiltered water line behind of Kirpal Bagh (Joginder Wala Bagh) Gujaran Wala Town Phase-III |  |  |  | Sh. S.D. Falwaria |  |  |  |  |  |  | Tis Hazari 87/2005 |  |  |  |  |  |  |  |  | Mrs. Shushma Sharma |  |  |  |  |  |  | 14.01.2008 |  |  |  |
| (viii) |  |  | D/o green belt in front of Bl. E to I in Ashok Vihar Phase-I SH. : C/o Cement Concrete tiles and moorum path in front of bl. E to I. |  |  |  | M/s Durga Const. Co. |  |  |  |  |  |  | Tis Hazari 216/04 |  |  |  |  |  |  |  |  | Sh. K.D. Sharma |  |  |  |  |  |  | 22.11.2008 |  |  |  |
| 11. |  |  | Details of Q.C. Lab. Tests, procedures |  |  |  |  |  | N.A. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12. |  |  | Fire fighting Equipments : Installed (Nos.) with Location |  |  |  |  |  | Not installed as yet |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13. |  |  | List of Soil Testing Laboratories |  |  |  |  |  | Are issued by E.M. Office |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14. |  |  | List of Approved Structural Consultants |  |  |  |  |  | Does not pertain to this office |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15. |  |  | Technical Circulars |  |  |  |  |  | Are issued by V.C., E.M., C.E. (Q.C.) and Vigilance Department |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 16. |  |  | Q.C. Circulars |  |  |  |  |  | Are issued by QAC, DDA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17. |  |  | List of Contractors, A, B, C, D categories |  |  |  |  |  | Pertains to CRB/DDA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 18. |  |  | RIS/ EIS/ EOT Cases & Completion Certificate |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| S.No |  |  | Name of Work |  |  | Agency |  |  |  |  | Agreement No. |  |  |  | EIS |  |  | RIS |  |  |  |  | SIS |  |  |  |  | Amount |  |  |  |  | EOT |
| (i) |  |  | D/o Yamuna River Front (West Bank) along Vijay Ghat (Pushta) S.H. : C/o Water body at Yamuna Pushta |  |  | M/s Amar Constn. Co. |  |  |  |  | 76/EE/ND-I/DDA/ 04-05 |  |  |  | -- |  |  | -- |  |  |  |  | -- |  |  |  |  | -- |  |  |  |  | Remarks C.C. to be recorded |
| (ii) |  |  | --DO— S.H. : C/o root-zone channel in Phase-I at Yamuna Pushta. |  |  | M/s Birender Constn. Co. |  |  |  |  | 36/EE/ND-1/DDA/04-05 |  |  |  | -- |  |  | -- |  |  |  |  | -- |  |  |  |  | -- |  |  |  |  | Remarks C.C. sent to competent authority for counter signed |
| (iii) |  |  | M/o Park/Plantation of Horticulture Wing under North Zone SH : Repair of Boundary Wall in M.D. Park (District Park) Lawrence Road |  |  | M/s S.V Construction Co. |  |  |  |  | 58/EE/ ND-1 DDA/ 06-07 |  |  |  | EIS No.I |  |  |  |  |  |  |  |  |  |  |  |  | Rs. 5412/- |  |  |  |  | EOT approved |
| (iv) |  |  | D/o Green belt along Block B to I Ashok Vihar Phase-I SH : P/L unfiltered water supply line in front of Block B to E |  |  | Sh. Rajinder Singh |  |  |  |  | 5/EE/ ND-1 DDA/ 07-08 |  |  |  | EIS No. I & II III IV V |  |  | - |  |  |  |  | - |  |  |  |  | Rs. 19,904/- Rs.40,630/- Rs.8205/- Rs.5494/- |  |  |  |  | EOT approved |
| (v) |  |  | D/o Yamuna river front (West bank along Vijay Ghat Pushta SH: Root Zone Channel (Water bodies) in Ph-I Yamuna Pushta |  |  | M/s Birender Construction Co. |  |  |  |  | 36/EE/ND-I/ DDA/04-05 |  |  |  | Revised EIS-I |  |  |  |  |  |  |  |  |  |  |  |  | Rs.1,48,462/- |  |  |  |  |  |
| (vi) |  |  | D/o Yamuna river front (West bank along Vijay Ghat Pushta SH : P/F Fabricated Huts (3 Nos) Pota Cabin at Yamuna Pushta |  |  | M/s Home Decorators |  |  |  |  |  |  |  |  | EIS-I |  |  |  |  |  |  |  |  |  |  |  |  | Rs.73,146/- |  |  |  |  | EOT Yet to be approved |
| (vii) |  |  | M/o Park/Plantation of Horticulture Wing under North Zone SH : Repair of Boundary Wall at Khojewala Park, Ashok Vihar, Phase-II. |  |  | M/S Bajrang Engg. |  |  |  |  |  |  |  |  | EIS I & II |  |  |  |  |  |  |  |  |  |  |  |  | 53,474/- |  |  |  |  | EOT yet to be approved |
| (viii) |  |  | M/o Park/Plantation of Horticulture Wing under North Zone SH : Repair of path and water supply line in Distt. Park at Pritam Pura. |  |  | M/S N.K. Enterprises |  |  |  |  |  |  |  |  | EIS I & II |  |  |  |  |  |  |  |  |  |  |  |  | 11,657/- |  |  |  |  |  |
| (ix) |  |  | D/o Janak wala Bagh at Bharat Nagar, Ashok Vihar, Phase-iv SH : C/O Red Bajri Path |  |  | Sh. Yashpal Singh |  |  |  |  |  |  |  |  | EIS-I |  |  |  |  |  |  |  |  |  |  |  |  | 13,443/- |  |  |  |  | EOT approved |
| 19. |  |  | List of approved rates of SE (P) |  |  |  |  |  | Are issued by Chairman Market Rate Approval Committee / Concerned SE (P) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 20. |  |  | Areas where services are handed over to MCD / DJB & Deficiency charges |  |  |  |  |  | N.A. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 21. |  |  | List of vacant flats / Shops / Keosk / Commercial / Residential Plots on the date of completion / development. |  |  |  |  |  | N.A. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 22. |  |  | Jurisdiction of C.E. / Map. EE wise |  |  |  |  |  | Asstt. Engineer-I - D/o land for Bio-diversity Park at Jharoda Mazra Wazirabad Phase-I & II Asstt. Engineer-II - D/o Park at Sandesh Vihar - C/o 336 Multistoreyed HIG Houses at Mukherjee Nagar SH : 96 Multi Storeyed HIG Houses i/c Pile Foundation and Internal Electrification. All complete Gr- II Asstt. Engineer-III - Shastri Nagar - 56 Bigha Park - Shastri Nagar Park - Gulabi Bagh - District Park - Sindhora Kalan Park - Faiz Road Park - Idgah Park Asstt. Engineer-IV - Mazdoor Wala Park at Lawrence Road - Rose Garden Park at Lawrence Road - Nepal Wala Bagh at Lawrence Road - Pahari Wala Bagh at Lawrence Road - MD Park at Lawrence Road |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 23. |  |  | Details of land handed over to Engineering Wing for development |  |  |  |  |  | 157 Acre for D/o Land Bio-Diversity Park at Jharoda Mazra PH-I is in progress and 300 Acre land for Bio-diversity Park at Jharoda Mazra Wazirabad Ph-II has been taken over by Engineering Wing. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 24. |  |  | Sanctioned Strength / In place / vacancy position of Regular Staff |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| S.No |  |  | Designation |  | Sanctioned Strength |  |  |  |  |  |  |  | Men in Position |  |  |  |  |  |  |  | Shortfall |  |  |  |  |  |  |  | Excess |  |  |  |  |
| 1. |  |  | E.E. © |  | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |  | -- |  |  |  |  |
| 2. |  |  | A.E. © |  | 5 |  |  |  |  |  |  |  | 4 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  | -- |  |  |  |  |
| 3. |  |  | A.A.O. |  | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |  | -- |  |  |  |  |
| 4. |  |  | Head Clerk |  | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |  | -- |  |  |  |  |
| 5. |  |  | Steno |  | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |  | -- |  |  |  |  |
| 6. |  |  | J.E. (C) |  | 12+1 |  |  |  |  |  |  |  | 13+1 |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |  | 1 |  |  |  |  |
| 7. |  |  | D/Man |  | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |  | -- |  |  |  |  |
| 8. |  |  | U.D.C. |  | 4 |  |  |  |  |  |  |  | 3 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  | -- |  |  |  |  |
| 9. |  |  | L.D.C. |  | 6 |  |  |  |  |  |  |  | 4 |  |  |  |  |  |  |  | 2 |  |  |  |  |  |  |  | -- |  |  |  |  |
| 10. |  |  | Daftry |  | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |  | -- |  |  |  |  |
| 11. |  |  | Peon |  | 4 |  |  |  |  |  |  |  | 4 |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |  | -- |  |  |  |  |
| 12. |  |  | S.C.D. |  | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |  | -- |  |  |  |  |

EXECUTIVE ENGINEER

ND-1, DDA