DELHI DEVELOPMENT AUTHORITY

ELECTRICAL DIVISION NO. 8

LIST OF ACTIVITIES

1. Details of Pending Final Bills & non-refund of Security Deposits.

Details of pending final bills for the quarter ending June, 2007

| Sl. No. | Name of Work | Agency | Agreement No. | Stipulated date of start Completion | Actual date of completion | Date of payment of final bill | Reasons for delay in payment of final bill |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. |

-------------------------------------------------------------------------NIL------------------------------------------------------------------------------------

Details of non-refund of Security Deposits for the quarter ending June, 2007

| Sl. No. | Name of Work | Agency | Agreement No. | Stipulated date of start Completion | Actual date of completion | Date of payment of final bill | Amount of Security Deposit deducted | Reasons for delay in refund of Security Deposit |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. |

-------------------------------------------------------------------------NIL------------------------------------------------------------------------------------

2. Present status of works.

List of works costing more than Rs. 2.00 lacs for the quarter ending June, 2007

| Sl. No. | Name of Work | Agency | Estt. Cost Tendered amount(in lacs) | Stipulated date of start Completion | Physical progress | Actual Date of completion | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. |
| 1. | A) Construction/Development Works C/o 320/258 MS houses SFS at Motia Khan SH: IEI of 66 flats Blk-1 Motia Khan | Goel Elect. Works | 17.41 16.69 | 18.9.03 17.3.06 | 60% | Work in progress |  |
| 2. | S/I of passenger lifts in Blk-1 comprising of 66 SFS flats in Motia Khan | Johnsons Lift Pvt. Ltd. | 31.80 26.41 | 12.1.06 11.10.06 | 100% | Work in progress |  |
| 3. | C/o 320/258 MS houses SFS at Motia Khan SH: S/I wetriser system in Blk-1 of 66 flats Motia Khan | S.S. Fire Protection Engineers | 6.47 5.75 | 11.3.06 10.7.06 | 85% | Work in progress |  |
| 4. | C/o 320/258 MS houses SFS at Motia Khan SH:S/I of fire alarm P.A. system in Blk-1, 66 SFS flats | S.K. Engineers | 2.51 2.80 | 2.6.06 1.9.06 | 100% | Work in progress |  |
| 5. | C/o 216 MIG DU’s MS at Pitampura (near TV Tower) SH: C/o 72 MIG DUs i/c sanitary installation, water supply, sewage, drainage, roads & paths and internal electrification Gr.I | Ved Prakash Mittal & Sons | 22.57 50.54 | 25.10.06 24.10.08 | 10% | Work in progress |  |
| 6. | C/o 216 MIG DU’s MS at Pitampura (near TV Tower) SH: C/o 144 MIG DUs i/c sanitary installation, water supply, sewage, drainage, roads & paths and internal electrification Gr.II & III | Winner Constn. Pvt. Ltd. | 45.18 73.01 | 14.12.06 13.12.08 | 10% | Work in progress |  |
| 7. | D/o Distt. Centre at Rajendra Place, Balance Dev. & Constn. Work SH: IEI of multilevel parking | S.K. Enterprises | 2.97 3.08 | 8.12.06 7.3.06 | NIL | Work in progress |  |
| 8. | Replacement of EPABX at Vikas Minar | Hi-tech Accurate Communication (P) Ltd. | 7.19 5.89 | 1.4.07 15.5.07 | 100% | Work in progress |  |
| 9. | S/I of DG Set and replacement of LT Panel at Vikas Minar SH: Supplying, errection, testing and commissioning of DG Set at Vikas Minar | Budhiraja Electricals | 25.09 21.52 | 22.2.07 21.5.07 | NIL | Work in progress |  |
| 10. | S/I of DG Set and replacement of LT Panel at Vikas Minar SH: Supplying, errection, testing and commissioning of LT Panel at Vikas Minar | Panun Entracon Pvt. Ltd. | 21.40 21.87 | 23.3.07 22.6.07 | 80% | Work in progress |  |
| 11. | C/o 560 SFS houses Cat.II in Blk-D Pkt-1, Shalimar Bagh a)IEI of 192 SFS DUs Gr.I b)IEI of 208 FS DUs Gr.II | Goel Elect. Goel Elect. | 23.27 18.77 22.21 20.33 | 27.12.02 26.6.05 5.1.03 4.7.05 | 70% 70% | Work in progress Work in progress |  |
| 12. | C/o 70 LIG DUs in Blk.BH Poorvi Shalimar Bagh SH:IEI | Cholia Elect. Works | 5.27 5.35 | 16.10.05 15.4.07 | 60% | Work in progress |  |
| 1. | B) Operation/Maintenance Works M/o Completed scheme of Nazul A/c I under SWZ SH: Annual Maintenance & operation of lifts at Blk-5 Rajendra Bhawan, Rajendra Place | Sky Lark (India) | 2.73 2.85 | 18.5.07 17.5.08 | 17% | Work in progress |  |
| 2. | M/o Completed scheme of Nazul A/c I under SWZ SH: A/R/M/O lifts at Blk. No.1 Rajendra Bhawan, Rajendra Place | Sky Lark (India) | 2.73 2.88 | 14.4.07 13.4.08 | 15% | Work in progress |  |
| 3. | Maintenance of Completed works (North Zone) SH: Annual maintenance of lifts at 320 MS flats at Motia Khan Blk. 2 & 5 | OTIS Elevator Co. (India) | 4.67 4.77 | 23.3.07 22.3.08 | 25% | Work in progress |  |
| 4. | Maintenance of Completed works (North Zone) SH: Annual maintenance & operation of DG Set, fire pumps and water supply pumps sets at 320 MS flats under SFS at Motia Khan Blk. 2 & 5 | N.K. Engg. Works | 3.66 3.61 | 21.1.07 20.1.08 | 50% | Work in progress |  |
| 5. | M/o completed scheme of Nazul A/c I under SWZ SH: Annual maintenance & operation of fire pump set, clear water pump set, 4 nos. DG Set in Blk. 1,2,4&5 and market at Rajendra Bhawan, Rajendra Place | N.K. Engg. Works | 3.80 3.72 | 21.1.07 20.1.08 | 50% | Work in progress |  |
| 6. | Maintenance of Completed works (North Zone) SH: Annual operation of lifts in Blk.2 & 5 Motia Khan | Sky Lark (India) | 6.40 6.67 | 3.12.06 2.12.07 | 50% | Work in progress |  |
| 7. | M/o completed scheme of Nazul A/c I under SWZ SH: Annual maintenance & operation of lifts at Blk. No. 2 Rajendra Bhawan Rajendra Place | Sky Lark (India) | 2.70 2.62 | 9.9.06 8.9.07 | 85% | Work in progress |  |
| 8. | M/o completed scheme of North Zone under Naz. A/c II SH: Annual maintenance & operation of programmable computerized musical fountain at Distt. Park Pitampura | S.K. Enterpirses | 2.98 3.05 | 9.5.07 8.5.08 | 20% | Work in progress |  |
| 9. | M/o office building at Vikas Minar SH: A/O/M of wet riser and sprinkler system | Fire Cool Engineers | 2.86 3.00 | 16.2.07 15.2.08 | 33% | Work in progress |  |
| 10. | M/o office building at Vikas Minar SH: A/O/M of suspended plateform | Sky Lark (India) | 2.43 2.58 | 6.3.07 5.3.08 | 30% | Work in progress |  |
| 11. | M/o office building at Vikas Minar SH: Comprehensive maintenance of lifts | Kone Elevator (India) Pvt. Ltd. | 18.01 17.45 | 11.6.06 10.6.07 | 100% | Work in progress |  |

3.  Projects held up due to Court Case

-----Respective Court with Case No.          		 -----Nil-----

-----Date of next hearing				-----Nil-----

4. Rain Water harvesting

---Already provided					N.A.

---Proposed						N.A.

5. Water bodies:

---identiftied, status & under encroachment		N.A.

6. Details of Deposit Works:

- in hand (b) Under approval

-Status							N.A.

7.Details of deviation in works:

Details of deviations in works for the quarter ending June, 2007

| Sl. No. | Name of work | Name of Agency | Amount (in lacs) | Deviation |
| --- | --- | --- | --- | --- |
| 1. | M/o Completed works (North Zone) SH: Annual maintenance of lift at 320 MS flats at Motia Khan Blk. 2 & 5 | OTIS Elevator Co. (India) Ldtd. | 1.14 | 26.34% above |
| 2. | M/o Completed Schemes of Nazul A/c I under SWZ SH: Annual maintenance & operation of lift at Rajendra Bhawan, Rajendra Place Blk. No. 2 | Sky Lark (India) | 0.47 | 18.54% above |
| 3. | M/o Completed Schemes of Nazul A/c I under SWZ SH: Annual maintenance and operation of lifts in Blk. No. 1 at Rajendra Bhawan, Rajendra Place | Sky Lark (India) | 0.75 | 27.45% above |
| 4. | M/o Completed Schemes of Nazul A/c I under SWZ SH: S/I of Cold Water Storage Tank and insulated hot water distribution pipe for solar water heating system in four flats | Solar Track System | 0.08 | 9.11% aobe |
| 5. | M/o Completed Schemes of Nazul A/c I under SWZ SH: Annual maintenance of lift at Shopping cum office complex in Blk. No. 4, Lift No. 3 at Rajendra Bhawan, Rajendra Place | Sky Lark (India) | 0.03 | 16.12% above |
| 6. | M/o Completed Schemes of Nazul A/c I under SWZ SH: Annual maintenance of lift at Slhopping cum office complex in Block No. 4, Lift No. 4 at Rajendra Bhawan, Rajendra Place | Sky Lark (India) | 0.09 | 20.69% above |
| 7. | M/o Office building at Vikas Minar SH: Annual maintenance of water filter cum purifiers | Raj & Co. | 0.02 | 7.21% above |
| 8. | M/o Office building Vikas Minar – Annual maintenance of EPABX | J.K. Communication | 0.44 | 24.86% below |
| 9. | M/o Pump set at various col,onies under North Zone SH: Operation & maintenance of clear water pump set & DG set at Blk. D Pkt.A Shalimar Bagh | Super System Engineers | 0.17 | 11.75% above |
| 10. | M/o Completed Scheme of Nazul A/c I under SWZ SH: Repairing of llights provided in Rose Garden for lighting of monuments Firoze Shah Kotla | Hi-tech Elngineers (Regd.) | 0.06 | 2.88% above |

8. Restricted Call of Tenders.

Details of Restricted Call of Tenders for the quarter ending June, 2007

| Sl. No. | Name of work | Name of Agency | Amount (in lacs) |
| --- | --- | --- | --- |

---------------------------------------------------------NIL-------------------------------------------------------------------

9. Rescinded Works:

Details of Rescinded Works – Status as on 30.6.2007

| Sl. No. | Name of Work | Agency | Agreement No. | Stipulated date of start Completion | Provisional extension granted upto | Date of rescission of work | Date of award of balance work | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. |

-------------------------------------------------------------------------NIL------------------------------------------------------------------------------------

10. Arbitration & related Court Cases.

Details of Court Cases pending at the end of June, 2007 – Services matters

| Sl. No. | File No. | Name of employee | Name of Court/Suit No. | Name of Panel Lawyer | Nature of case | Present position | Next date of hearing | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. |
| 1. | F.1(476)95/IC/Legal | Sh. Om Prkash, Wireman W/C ® V/s DDA | Distt. Court RCA 11/2000 | Sh. Ashish Sharma | Transfer of W/C Staff to MCD | Arguments continued | 13.7.07 | - |

Details of Court Cases pending at the end of June, 2007 – (Works)

| Sl. No. | File No. | Name of Work | Name of Agency | Name of Court/Suit No. | Name of Panel Lawyer | Nature of case | Present position | Next date of hearing | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9 | 10. |
| 1. | F21(122)1999/HC/Legal | C/o 448 MIG DUs at Pkt. KD Pitampura SH: IEI of 356 DUs in Gr. II | Bumbrah Elect. Co. V/s DDA | High Court CWO 2561/98 | Sh. D.S. Mahendru | Nil Arbtrn. Award challenged by agency in Court. | Argument continued | 24.10.07 |  |
| 2. | F12(16)1999/TC/Legal | C/o 480 LIG houses at Pkt. KD Pitampura SH: IEI | R.K.Aneja V/s DDA | Distt. Court 1996 A/95 | Sh. S.S. Mittal | Suit file for recovery of Rs. 97610/- levied as compensation under Clause 2 of the Agrelement | Argument continued | 7.9.07 |  |
| 3. | F12(429)06/HC/Legal | Electrification of plot No. 4 Community Centre Motia Khan | Rajesh Projects India Pvt. Ltd. V/s BSES Rajdhani Power Ltd. & others | WP©No. 8212/06 | Sh. Jag Mohan Sabherwal | Electrification of Community Centre Motia Khan | Counter statement filed | 5.7.07 |  |
| 4. | F21(221)96/HC/Legal | D/o land at JJR Colony Jahangirpuri SH: S/I of storm/sewage pumps | Gita Pumps V/s DDA & MCD | OMP No. 1/96 | Sh. Bhupesh Narula | Arbitration award challenged | Argument continued | 10.7.07 |  |

11. Details of Q.C. Lab Tests, procedures 			N.A.

12. Fire fighting Equipments (installed with locations):

| Sl. No. | Location | Electric driven pumps | Diesel driven pumps | Jocky pumps | Fire extinguishers |
| --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. |
| 1. | Rajendra Bhawan, Rajendra Place | 100 HP – 2 Nos. | 100 HP – 1 No. | 20 HP – 1 No. | 7 Nos. |
| 2. | Motia Khan (MS housing) | 75 HP – 1 No. | 100 HP – 1 No. | 20 HP – 1 No. | 5 Nos. |
| 3. | Jhandewallan | 75 HP – 2 Nos. | 75 HP – 1 No. | 15 HP – 1 No. | 2 Nos. |
| 4. | Vikas Minar | 100 HP – 2 Nos. | 100 HP – 2 Nos. | 25 HP – 2 Nos. | 56 Nos. |

13. List of Soil Testing Laboratories 				N.A.

14. List of Approved Structural Consultants 			N.A.

15. Technical Circulars					N.A.

16. Q.C. Circulars						N.A.

17. List of Contractors A,B,C,D categories			N.A.

18. RIS/EIS/EOT cases & Completion Certificate:

Details of EIS/RIS for the quarter ending June, 2007

| Sl. No. | Name of Work | Name of agency | Amount (in lacs) |
| --- | --- | --- | --- |
| 1. | 2. | 3. | 4. |
| 1. | M/o Pump set at various colonies under North Zone (SH: Annual operation & maintenance of clear water supply pump set at 656 MIG houses at Jahangirpuri | Shiv Electric | 0.07 |
| 2. | M/o Completed works (North Zone) SH: Annual maintenance and operation of DG set, fire pumps and water supply pump set at 320 MS flats under SFS at Motia Khan Block No. 2 & 5 | N.K. Engg. Works | 0.15 |
| 3. | M/o Office building Vikas Minar (SH: Repair of Automation panel and replacement of flow switch defector of fire fighting system | Fire Cool Engineers | 0.10 |
| 4. | M/o Completed Scheme of Nazul A/c I under SWZ SH: Repairing of lights in Rose Garden for lighting of monuments Firoze Shah Kotla | Hi-tech Engineers (Regd.) | 0.05 |

Details of EOT cases for the quarter ending June, 2007

| Sl. No. | Name of Work | Agency | Agreement No. | Estt. Cost Ten.Amt. | EOT granted without levy of compen- sation | EOT granted with levy of compensa- tion | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. |
| 1. | M/o Completed Scheme of Nazul A/c I under SWZ SH: Providing compound lighting in the lawns of DDA officers’ flats at Bhagwan Dass Road | Hi-tech Engineers (Regd.) | 87/2006-07 | 2.57 2.05 | 12.4.07 to 19.4.07 | - |  |
| 2. | M/o office building at Vikas Minar SH: Annual maintenance of DG Set | Lloyds Enterprises | 106/2005-06 | 0.56 0.55 | 27.3.07 to 2.4.07 | - |  |
| 3. | M/o Completed Works (NZ) SH: Annual maintenance of lifts at 320 MS flats Motia Khan | OTIS Elevator Co. (India ) Ltd. | 75/2005-06 | 4.19 4.33 | 19.12.07 to 18.3.07 | - |  |
| 4. | M/o Office building at Vikas Minar SH: Annual maintenance of water filter cum purifiers | Raj & Co. | 103/2005-06 | 0.25 0.25 | 26.3.07 to 16.5.07 | - |  |
| 5. | M/o Pump sets at various colonies under NZ SH: Operation & maintenance of clear water pump sets and DG sets at Blk. D Pkt. A Shalimar Bagh | Super System Engineers | 98/2005-06 | 1.45 1.44 | 7.3.07 to 19.4.07 | - |  |
| 6. | M/o pump sets at various colonies under NZ SH: Running, operation & maintenance of clear water pump set, DG sets, submersible P/sets & street lighting at 560 SFS houses in Blk. C&D Shalimar Bagh | Super System Engineers | 90/2005-06 | 1.98 1.96 | 1.2.07 to 25.3.07 | - |  |

19. List of approved rates of SE(P)				N.A.

20. Areas where services are handed over to MCD, DJB

& Deficiency Charges					N.A.

21. List of vacant flats/Shops/Kiosks/Commercial/

Residential Plots on the date of completion/

Development.						N.A.

22.Jurisdiction of C.E./Map. EE wise				N.A.

23.Details of land handed over to Engineering Wing

For development.						N.A.

24.Sanctioned Strength/In place/vacancy

Position of Regular Staff					N.A.

Sent to Director (System) through E-mail at

1) dda tender @ dda.org.in           2) dir system @ dda.org.in