LIST OF ACTIVITIES

NORTH ZONE, DDA

Circle:-	Civil circle-7						DIVISION:-	Northern Division WD-5

| 1. | Details of Pending Final Bills & non-ref, of Security Deposits. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Name of Work | Agencies | Agmt. No. | Esst. Cost. Tender Cost | Stipulated | Remarks |
|  |  |  |  |  | D.O.S D.O.C |  |
| i. | M/o Completed Scheme of Nazul A/c-II under SWZ SH: Boring of tubewell one no by DTH/RR machine at Booli Bhatiyari Park at Ridge | M/s S.B. Tubewell Engineers | 2/EE/WD-5/ 06-07 | 1,90,937 2,85,900 | 20.05.06 19.06.06 | Final bill has been prepared Agency not turned up for accepting the bill |
| ii. | Protection of D.D.A. Land SH: C/o Randum rubble masonry on vacant land under jurisdiction of CC-5 | M/s Tara Chand Sumit Construction Co. | 13/EE/WD-5/DDA/05-06 | 893801 591219 | 28.11.05 27.05.06 | Work has been completed payment of 7th R/A held up as per instruction of higher authorities. |
| iii. | M/o of Vikas Minar SH: P/F floor tiles on 5th 6th & 7th floor at Vikas Minar | M/s S.K. Mittal & Co. | 34/EE/WD-5/DDA/05-06 | 487418 290090 | 26.03.05 25.04.05 | Concerned MB’s with vigilance brand in other case |
| iv. | All due securities are being refunded on the request of respective Agencies |  |  |  |  |  |

| 2 | Present statues of works as on 31.07.07 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S. No. | Name of Work | Estt. Cost Tendered Cost |  | D.O.S D.O.C | Progress up to previous month | Progress during this month | Up to date progress | Remarks |
| i. | D/O Distt. Centre at Rajindra Place (Bal. Dev. & Constn. Work). SH: C/o parking lot ‘D’. Agency: M/s Tara Chand Sumit Const. Co. | 8342464.00 8714478.00 |  | 09.02.06 08.08.06 | 75% | 5% | 80% | The work could not be taken up due to nonavilability of 25mm dia steel. Now the same is available and agency has been asked to take up the work accordingly. Show cause notice has been issued. |
| ii. | M/o Vikas Minar SH : Replacement of basement flooring for parking at Vikas Minar. Agency : Sh. M/s Tara Chand Sumit Const. Co. | 1236568.00 1841908.00 |  | 14.10.06 13.04.07 | 18% | — | 18% | Show cause notice has been issued. |
| iii. | M/o Vikas Minar SH: Cleaning & mopping of toilets, pantries, spittoons, dustbin, stair case, corridors, dusting of venation blind furniture etc. at all floors of Vikas Minar Agency : Sh. Rajesh Kumar | 292378.00 504000.00 |  | 19.02.07 10.08.07 | 53% | 35% | 88% | Work in Progress |
| iv. | M/o Vikas Minar SH : Repairing of office furniture i.e. Chairs tables, Sofa, Almiraha etc. (Wooden & Still) Agency : M/s Indian Trading Co. | 482406.00 511649.00 |  | 14.10.06 13.04.07 | 80% | 20% | 100% |  |
| v. | M/o Vikas Kuteer SH : Scavenging and cleaning of office building, open area and toilets at Vikas Kuteer Agency : M/s S. V. Enterprises | 40077.00 56400.00 |  | 01.06.07 31.12.07 | 20% | 10% | 30% | Work in progress |
| vi. | Special Repair at Vikas Minar SH : P/F Safety net debris arrestor at Vikas Minar Agency : M/s Sandeep Traders | 407767.00 546367.00 |  | 19.04.07 18.07.07 | 60% | 40% | 100% | Test report awaited |
| vii. | M/o Vikas Minar SH : Soil investigation to assess liquefaction potential of sub-strata for Vikas Minar, Corner/ periphery. Agency : M/s Magma Soil & Foundation consultant Pvt. Ltd. | 338000.00 268000.00 |  | 10.05.07 24.05.07 | 100% | — | 100% |  |
| viii. | M/o Vikas Minar, SH : Repair of Kota/ Marble Stone Flooring and tiles works at Vikas Minar Agency : M/s Harvender Singh | 264192.00 142933.00 |  | 01.06.07 30.08.07 | — | — | — | Agency has not turned up after award of work hence earnest money and performance guaranty forfeited |
| ix. | M/o Completed scheme of N/A. II under SWZ. SH : P/F G.I. barbed wire fencing along proposed passage for local people of Dasghara Village and Const. of wicket gates. Agency : M/s P.K. Engineer | 136053.00 141210.00 |  | 10.07.07 09.08.07 | — | — | — | Working in progress |
| x. | Special Repair of Vikas Minar. SH : Rehabilitation of RCC column and beams and other RCC members of Vikas Minar. Agency : M/s Cembond Constructions. | 5849019.00 6997284.00 |  | 18.01.07 14.04.08 | — | — | — | Scaffolding work in progress |
| xi. | M/o completed scheme of Nazul A/c-II under SWZ. SH : Repair of broken boundary wall and closing of missing link at R Block Park, New Rajindera Nagar. Agency : M/s Amit Builders | 237630.00 219873.00 |  | 15.07.07. 14.09.07 | — | — | — | Work in progress |
| 3. | Projects held up due to Court Case |  |  |  |  |  |  |  |
|  | -- Respective Court with Case No. -- Date of Next Hearing |  | Nil |  |  |  |  |  |
| 4. | Rain Water Harvesting |  |  |  |  |  |  |  |
|  | -- Already Provided -- Propose |  | Nil |  |  |  |  |  |
| 5. | Water bodies |  |  |  |  |  |  |  |
|  | -- identified, status & under encroachment. |  | Nil |  |  |  |  |  |
| 6. | Details of Deposit Works: |  |  |  |  |  |  |  |
|  | - in hand (b) Under approval - Status |  | Nil |  |  |  |  |  |

| 7. | Details of deviation in works: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | (a) Undertaken. Nil (b) Proposed (In principal approval) |  |  |  |  |  |  |
| S No. | Name of work | Agency | Agg. No. | Tendered | Total Work Done | Deviation | Remarks |

| 8 | Restricted Call of tenders |
| --- | --- |

LIST OF WORK ORDER FOR THE YEAR 2007-08

| W.O. No. |  |  |  | Name of Work |  | Estt. Cost | Work order amount |  |  | Sanctioned by | Time allowed |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1/ EE/WD-5 DDA/ 0 7 -08 |  |  |  | M/O Staff Qtrs. At Rajinder Nager SH: Repair and renovation work in Bungalows and Barat Ghar at Rajinder Nagar, |  | Rs, 4,73,800/- | Rs. 5,95,583/- |  |  | CE (SWZ) DDA | 38 days |  |
| 2/EE/WD-5- DDA/07/08 |  |  |  | M/o Vikas Minar. SH: Providing temporary protection from falling loose concrete. |  | Rs. 1,60,459/- | Rs. 1,53,780/- |  |  | S.E./CC-5/DDA | 25 days |  |
| 3/ EE/ WD-5/ DDA/07-08 |  |  |  | M/o Vikas Minar. SH: Alteration of existing partition frame resistant partition of Director (IS) Alterations. |  | Rs. 5,45,683/- | Rs. 5,78,328/- |  |  | CE (SWZ) DDA | 15 days |  |
| 9. |  |  |  | Rescinded Works. |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Nil |  |  |  |  |  |  |
| 10. |  |  |  | Arbitration & related Court Cases |  |  |  |  |  |  |  |  |
| a) |  |  |  | Arbitration |  | Nil |  |  |  |  |  |  |
| b) |  |  |  | Court Cases |  |  |  |  |  |  |  |  |
|  | S. No. |  | Description |  | Agency |  |  | Name of Court | Name of panel lawyer |  | Next dt. Of Hearing |  |
|  | 1 |  | 2 |  | 3 |  |  | 4 | 5 |  | 6 |  |
|  | i. |  | D/o J.J Colony kalkaji. Sh: P/L Dense carpet concrete work in J.J. Colony |  | Sh. Satya Prakash & Brothers |  |  | High Court. | Sh. D.S. Mhendroo |  | 06.09.2007 |  |
|  | ii. |  | C/o 504 SFS Cat. II houses at Sukhdev Vihar. Sh. C/o 192 Du’s i/c int. Development. |  | M/s. Bhartya Const Co. |  |  | High Court. 208/97 | Sh. B.B. Sharma |  | 31.07.2007 |  |
|  | iii. |  | C/o 232/108 SFS Cat. II houses at Paschim Vihar. |  | M/s/ Hindustan Prefab Ltd. |  |  | High Court. 320/96 | Mrs. Sangeeta Chandra |  | Regular hearing |  |
|  | iv. |  | C/o 232/124 SFS houses at Paschim Vihar. |  | M/s/ Hindustan Prefab Ltd. |  |  | High Court. CS (OS) 1965/96 | C. Mohan Rao |  | Recovery suit filed date aviated |  |
|  | v. |  | C/o 504 SFS Houses at SukhDev Vihar. Sh: Pile foundation. |  | M/s Ground Engineer Co. (P) Ltd. |  |  | High Court 67-A/96 Ex. 47/2002 | Mrs. A. Salwan |  | Regular Hearing |  |
|  | vi. |  | C/o M.S.O. Bldg for DDA office SH: Bldg. & basement portion |  | M/s. Layall & Co. |  |  | High Court. FAO (05) 243/92 | Mrs. A. Salwan |  | Regular Hearing |  |
|  | vii. |  | C/O 160 SFS at Sukhev Vihar. |  | Sh. K.K. Rathi |  |  | High Court. 179/92 | Mrs. A. Salwan |  | Case decided and copy of judgment awaited |  |
|  | viii. |  | M/o Completed scheme under SWZ. Sh. Repairing of road of Janakpuri Paschim Vihar. |  | Sh. S.P. Gupta |  |  | High Court 558/2002 | K. K Chawla |  | 30.08.2007. |  |
|  | ix. |  | Ray Provision of passes to Village Dsagarha through ridg. |  | Residents of Village Dasgrah by DDA |  |  | High Court. | Sh. Rajeev Bansal |  | 14.08.2007 |  |
|  | x. |  | C/o 864 LIG Houses at Hastsal Pkt-‘B’. SH: C/o 252 LIG Houses including internal water supply installation and internal development. |  | M/s Arkey Engineers Co. |  |  | Tis Hizari Court. | Sh. Rohit Jain |  | 17.08.2007 |  |
|  | xi. |  | Destitutinal area D- Block Janakpuri |  | Vice Chairman V/s Dir. Revenue & other |  |  | Tis Hizari Court. | Sh. H.K.L. Seghal. |  | 13.02.2008 |  |
|  | xii. |  | C/o 504 SFS Cat. II houses at Sukhdev Vihar. Sh. C/o 192 Du’s i/c int. Development. |  | M/s Bhartiya Const. Co. |  |  | High Court. FAO (OS) 273/97 | Sh. B.B. Shrama & Jagmohan Sabharawal. |  | 30.10.2006 |  |
|  | Xiii |  | C/o 504 SFS Cat. II Houses at Sukhdev Vhiar Sh: C/o 152 MIG/ Cat. II SFS |  | Sh. S.S. Jetly |  |  | High Court 275/01 | Ms. A Salwan |  | 20.11.2007 |  |
|  | xiv. |  | C/o Shopping Center at Nehru Place on Plot No. 42 |  | C. Lal Gupta. |  |  | High Court. | Mrs. A. Salwan |  | 13.08.2007 |  |
|  | 11. | Details of Q.C Lab. Tests, Procedures |  |  | N/a |  |  |  |  |  |  |  |
|  | 12. | Fir fighting Equipments: Installed (Nos) with Location |  |  | N/a |  |  |  |  |  |  |  |
|  | 13. | List of Soil Testing Laboratories |  |  | N/a |  |  |  |  |  |  |  |
|  | 14. | List of Approved Structural Consultants |  |  | N/a |  |  |  |  |  |  |  |
|  | 15. | Technical Circulars |  |  | N/a |  |  |  |  |  |  |  |
|  | 16. | Q.C. Circulars |  |  | N/a |  |  |  |  |  |  |  |
|  | 17. | List of Contractors, A, B, C, D categories |  |  | N/a |  |  |  |  |  |  |  |

| 18 |  | RIS/ EIS/ EOT Cases & Completion Certificate |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S. No. |  | Name of Work |  | Agency |  | Agreement | EIS | RIS | SIS | Amount | EIT |  |
| 19. |  | List of approved rates of SE(P) |  |  | Are issued by Chairman Market rate approval committee/Concerned SE (P) |  |  |  |  |  |  |  |
| 20 |  | Areas where serviced are handed over to MCD/ DJB & Deficiency charges. |  |  |  |  |  |  |  |  |  |  |
| 21 |  | List of vacant flats/ Shops/ Keosk/ Commercial/ Residential Plots on the date of completion development. |  |  | - Distt. Center Rajinder Place 2 nos shops bearing shope no. 103 & 145 - Hog market Rajindera Place 3 nos shops bearing shops no 193, 194 & 196 - Janta Flats Toda Pur 5 nos flats bearing flat nos 103, 113, 83, 86, & 94 |  |  |  |  |  |  |  |
| 22. | Jurisdiction of C.E/Map. EE wise |  | Asstt. Engineer- I - M/o Vikas Minar office building floor 11 to 21 - M/o Vikas Kuteer Barrack No. - 6 |  |  |  |  |  |  |  |  |  |

|  | Asstt. Engineer- II (i) M/o Vikas Minar office building floor basement to 10 floor |
| --- | --- |

|  | Asstt. Engineer- III - M/o of staff quarter at Rajindera Nagar, Jaidev Park, Concrete House Karol Bagh, Dev Nagar & Bagh Rao Ji - D/o Anand Parbhat area - M/o LSC 2,4 & 20 and CSC 22 at New Rajindera Nagar - M/o MOR land pocket 7,8,9 at New Rajindera Nagar - D/o of land at 8A WEA Karol Bagh |
| --- | --- |

|  | Asstt. Engineer- IV - Distt. Center of Rajindera Place - Bhooli Bhatyari Park at Ridge - “R” Block Park at New Rajindera Naga - Rock Garden at Patel Nagar - Satya Park Naraina Industrial area Phase-II - Maha Raja Aggarsen Park Inder Puri - N.H.P. Park Naraina - Janta Flats Toda Pur - Golden Park |
| --- | --- |
|  | Asstt. Engineer- V (i) M/o officers Staff Flats at Bhagwandas Road |

| 23. | Details of land handed over to Engineering Wing for development | Nil |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 24. | Sanctioned Strength/In place/ vacancy position of Regular Staff |  |  |  |  |
| S. No. | Designation | Sanctioned Strength | Men in Positions | Shortfall | Excess. |
| (i) | Executive Engineer | 1 | 1 | — | — |
| (ii) | Assistant Engineer | 5 | 6 | — | 1 |
| (iii) | Junior Engineer | 17 | 10 | 7 | — |
| (iv) | Divisional Accountant | 1 | 1 | — | — |
| (v) | Head Clerk | 1 | 1 | — | — |
| (vi) | UDC | 5 | 5 | — | — |
| (vii) | LDC | 7 | 2 | 5 | — |
| (viii) | Assistant Cashier | 1 | 1 | — | — |
| (ix) | Steno | 1 | — | 1 | — |
| (x) | D/Man | 1 | 1 | — | — |
| (xi) | Peon | 4 | 3 | 1 | — |

EXECUTIVE ENGINEER

WD-5/DDA