As on 31.08.2007

ELECTRICAL DIVISION NO.-10

PRESENT STATUS OF WORKS (RS. 2 LACS & ABOVE )

| S.No. | Name of work | Agency | Estt. Cost | Tend. Cost | DOS as per Agmt. | DOC as per Agmt. | Progress |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Phy. | Fin. |  |
| 1. | D/o Millennium park along with ring road between ISBT Sarai Kale Khan & Bhario Road. (SH: Supply & installation of parking & installation of parking lights in Zone-4 ) Agmt. No. 19/EE/Elect.-10/2006-2007 | M/s Rohit Enterprises | Rs. 669963/- | Rs. 585463/- | 19.11.2006 | 18.02.2007 | 100% | 100% | Work completed |
| 2. | M/o various scheme in EZ under NA-II SH: Running, operation & maintenance contract of submersible pump sets & St. lighting at facility cum service centre at Gokulpuri. Agmt. No. 22/EE/Elect.10/2006-2007 | M/s Alliance Consultants & Engineering | Rs. 217896/- | Rs. 180030/- | 05.12.2006 | 04.12.2007 | 70% | 50% | Work in progress |
| 3. | M/o various scheme in EZ under NA-II SH: RMO land scape lighting at CBD Shahdara Agmt. 26/EE/Elect.-10/2006-2007 | M/s Metro Electric Co. | Rs. 324857/- | Rs. 244987/- | 03.03.2007 | 02.03.2008 | 40% | 25% | Work in progress |
| 4. | M/o various scheme in EZ under NA-II SH:RMO of sub. Station DG set & lighting at Millenium park Agmt. No. 28/EE/El.-10/2006-2007 | M/s P.K. Pumps Engineering Enterprises | Rs. 833338/- | Rs. 832908/- | 15.03.2007 | 14.03.2008 | 40% | 30% | Work in progress |
| 5. | M/o various scheme in EZ under NA-II SH: Running, operation & maintenance contract of sub. Pump set, st. lighting of facility cum service centre at Seemapuri in ‘H’ block pkt.1,2,3,4 &5 Agmt. No. 30/EE/Elec.-10/2006-2007 | M/s Hindustan Enterprises | Rs. 227994/- | Rs. 191350/- | 26.03.2007 | 25.03.2008 | 40% | NIL | Work in progress |
| 6. | M/o various scheme in EZ under NA-II in South East Zone SH: Repair & maintenance of submersible pump sets in various sites under Elect. Division No.-10 in South East Zone Agmt. No. 05/EE/Elect.-10/2007-2008 | M/s Metro Electric Co. | Rs. 336064/- | Rs.288725/- | 03.05.2007 | 02.05.2008 | 30% | 20% | Work in progress |
| 7. | M/o various colonies in SEZ (SH: Running, operation & maintenance contract of booster pump set, sub. Pump set, DG set at 2408 one room tenements at Pkt.11 at Jasola.) Agmt. No. 09/EE/Elect.-10/2007-2008 | M/s Alliance Consultants & Engineering | Rs. 238914/- | Rs. 231140/- | 09.06.2007 | 08.06.2008 | 25% | 15% | Work in progress |
| 8. | M/o various scheme under NA-II on SEZ (SH: Annual Running & operation of submersible pump sets, fountain & maintenance of associated U/G cables at Millenium park. Agmt. No. 10/EE/Elect.-10/2007-2008 ) | M/s Cholia Electric Co. | Rs. 500596/- | Rs. 435733/- | 15.07.2007 | 14.07.2008 | 30% | 25% | Work in progress |
| 9. | C/o 96 MIG & 96 LIG DU’s in Dilshad Garden block ‘R’ in Group –IV ( Actually 100 MIG & 100 LIG DU’s to be constructed ) SH: IEI Agmt. No. 29/EE/Elect.-10/2006-2007 | M/s Shubham Electricals | Rs. 3560150/- | Rs. 4934475/- | 26.03.2007 | 25.09.2009 | 12% | NIL | Work in progress |