DELHI DEVELOPMENT AUTHORITY

ELECTRICAL DIVISION NO.4, ROHINI, DELHI-110085

DETAILS OF PENDING FINAL BILLS DURING THE YEAR 2007-08 FOR THE QTR. ENDING JUNE’2007

| S.No. | Name of work | Agency | Agreement No. | Stipulated Date of Start/ Completion | Actual Date of Completion | Date of Payment of Final Bill | Reasons for delay in payment of Final Bill |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. |
| -----------------------------------------------------------------------------------Nil Report-------------------------------------------------------------------------------- |  |  |  |  |  |  |  |

-----sd----

Executive Engineer (E)

Electrical Division No.4, DDA,

Rohini, Delhi-110085.

DELHI DEVELOPMENT AUTHORITY

ELECTRICAL DIVISION NO.4, ROHINI, DELHI-110085.

DETAILS OF NON-REFUND OF SECURITY DEPOSIT DURING THE YEAR 2007-08 FOR THE QTR. ENDING JUNE’2007

| S.No. | Name of work | Agency | Agreement No. | Stipulated Date of Start/ Completion | Actual Date of Completion | Amount of Security Deposit | Date of Payment Final Bill | Reasons for Delay in refund of Security Deposit |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. |
| ------------------------------------------------------------------------------------------Nil Report------------------------------------------------------------------------- |  |  |  |  |  |  |  |  |

-----sd----

Executive Engineer (E)

Electrical Division No.4, DDA,

Rohini, Delhi-110085.

DELHI DEVELOPMENT AUTHORITY

ELECTRICAL DIVISION NO.4, ROHINI, DELHI-110085

PRESENT STATUS OF WORKS AS ON 30.06.07

| S.No. | Name of work | Agency | Agreement No. | Estt. Cost/ Tendered Amount | Stipulated Date of Start/ Completion | Actual date of completion | Present upto date progress of work |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | (in %) | in lacs of rupees |  |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. |
| 1. | C/O 240 MIG Houses near Madipur Village (SH:- I.E.I) | M/S Goel Electricals | /EE/ ED-4/DDA 2003-04 | 28,72,970/- 24,87,380/- | 29.04.2004 28.10.2006 | Work in progress | 75% | 18.81 | Allottement work of DU’S in progress |
| 2. | C/O 200 LIG Houses in Pkt. I Block ‘E’ Sector –18 Rohini (SH;- I.E.I of 200 DU’s) | M/S Goel Electricals | 06/EE/ED-4/DDA/2005-06 | 16,07,865/- 14,53,464/- | 28.04.2005 27.11.2006 | 12.02.2007 | 40% | 05.73 | Work closed due slow progress of civil work. Tenders for the remaining work are yet to be invited. |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. |
| 3. | C/O 208 LIG Houses at Pkt. GH-3 in G-17 Area Paschim Vihar (SH:-I.E.I pf balance work – Recoverable from M/S Bharat Electric Co.) | M/S Metro Electric Co. | 44/EE/ED-4/DDA/2006-07 | 9,08,524/- 18,20,316/- | 26.11.2006 25.08.2007 | Work in progress | 60% | 10.59 | Allottement work of DU’s in progress |
| 4. | M/O Completed Schemes under Nazul A/C-II of S.W.Z (SH:- P/F of additional path lights on 6 mtrs. G.I. Poles at DDA Park Madipur Lake) | M/S Adrash Electricals | 07/EE/ED-4/DDA/2006-07 | 2,82,970/- 2,42,638/- | 07.05.07 06.06.07 | 06.06.07 | 100% | 2.50 | Work completed |

-----sd----

Executive Engineer (E)

Electrical Division No.4, DDA,

Rohini, Delhi-110085.

DELHI DEVELOPMENT AUTHORITY

ELECTRICAL DIVISION NO.4, ROHINI, DELHI-110085

DETAILS OF DEVIATIONS  ----WORKS DURING 2007-08 FOT THE QTR. ENDING JUNE’2007

| S.No. | Name of work | Agency | Agreement No. | Estt. Cost (In rupees) | Tendered Amount (In rupees) | Amount of deviation approved (In rupees) | Amount of deviation proposed | Reference of principle approval accorded by competent authority |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8, | 9. |
| 1. | M/O Completed Schemes under Nazul A/C-II under S.W.Z (SH:- R/M/Oof pump sets and park lights at District Park Inder Puri) | M/S S.K Entrprises | 118/ EE/ED-4/DDA/05-06 | 64,628/- | 63500/- | (+) 9,460/- | -- | -- |
| 2. 3. 4. 5. | M/O Completed Schemes under Nazul A/C-II under S.W.Z (SH:- P/F of additional path lights on 6 Mtr. GI poles at DDA Park Madipur) M/O Completed Schemes under Nazul A/C-II under S.W.Z (SH:- Repairs and rewinding and lifting and lowering of submersible pump sets under Hort. Divn No.-8) M/O Completed Schemes under Nazul A/C-II under S.W.Z (SH:- R/M/O of pump sets, park lights at Tagore Garden & Shivaji Park ESI Hospital) M/O Completed Schemes under Nazul A/C-II under S.W.Z (SH:- R/M/O of pump sets & park lights at ‘M’ Block & ‘C’ Block Vikas Puri) | M/S Adrash Electricals M/S Alliance Construction & Engineers M/S Rohit Enterprises M/S Pumps Engg. & Associates | 07/ EE/ED-4/DDA/07-08 22/ EE/ED-4/DDA/06-07 17/ EE/ED-4/DDA/06-07 79/ EE/ED-4/DDA/05-06 | 2,82,970/- 1,91,230/- 76,760/- 1,64,460/- | 2,42,638/- 1,55,163/- 46,530/- 1,15,075/- | (+) 6,856/- (-) 5,069/- (+) 7,025/- (+) 80,415/- | -- -- -- -- | -- -- -- -- |

--sd--

EE/ED-4

DELHI DEVELOPMENT AUTHORITY

ELECTRICAL DIVISION NO.4, ROHINI, DELHI-110085

DETAILS OF RESCINDED WORKS               STATUS AS ON 30.06.2007

| S.No. | Name of Work | Agency | Agreement No. | Stipulated Date of Start/ Completion | Provisional EOT granted upto-- | Date of Rescission of work | Date of award of Balance Work | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. |
| 1. | C/O 208 LIG Houses at Pkt.GH-3 IN G-17 Area Paschim Vihar (SH:- I.E.I) | M/S Bharat Electric Co. | 40/EE/ ED-4/DDA/ 2003-04 | 16.11.2003 15.05.2006 | 15.10.2006 | 17.08.2006 | 16.11.2006 | ----- |

-----sd----

Executive Engineer (E)

Electrical Division No.4, DDA,

Rohini, Delhi-110085.

DELHI DEVELOPMENT AUTHORITY

ELECTRICAL DIVISION NO.-4, ROHINI, DELHI-110085.

STATEMENT OF PENDING COURT CASES FOR THE MONTH ENDING JUNE’2007

| S.NO | SUIT NO. | FILE NO. | NAME OF SCHEME AGREEMENT NO. | NAME OF AGENCY | NAME OF PANEL LAWYER | Date of Entrust-ment | NATURE OF CASE | PRESENT POSITION | Last date of hearing | NEXT DATE OF HEARING |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 62/95 Delhi High Court | F2 (131) 95HC/ Legal | C/O 832 EWS Houses in Pkt. B-5 & C-1 Sector XI, Rohini (SH:I.E.I) Ag. No.01/EE/ ED-4/DDA/89-90 | M/ Prominent Electric Works | Sh. Ashutosh Sharma | 06.09.05 | Challenge of Arbitration Award | Arguments are in process. | 03.05.07 | 01.11.07 |
| 2. | 17A/95 Delhi High Court | F2 (203) 95/HC/ Legal | C/O 320 MIG Houses Blk.’A’ Pkt.1, 2,3 &4 Sector 18 Rohini (SH: I.E.I) Ag. No.01/EE/ ED-4/DDA/86-87 | (---do---) | Ms. Amita Singh | 07.01.05 | Judgment of single bench of Justice Sh.A.K.Sikri set aside by the double bench DHC | Orders from High Court are awaited. | -- | Date yet to be fixed |
| 3 | Ex252/2000 Delhi High Court | F2 (166) 2001/ HC/ Legal | C/O Local Shopping Centre at Blk. ‘A’Naraina Vihar Ring Road (SH:I.E.I) Ag. No.23/EE/ ED-4/DDA/98-99 | M/S Metro Electric Co. | Sh. Banke Bihari Sharma | 29.07.05 | Challenge of Arbitration Award | The case has been decided in favour of DDA for Old Act. Appeal filed against Arbitrator under Old Act on 30.04.06 | 05.04.07 | 24.08.07 |
| 4 | WP(C) 17678/04 Delhi High Court | F12 (299) /04/ HC/ Legal | Electrification of DDA colonies. | DDA V/s 1.DERC 2.BRPL 3.BYPL 4.NDPL | Sh. Pawan Mathur |  | Petition for non-payment of 50% DDA Share to the licensee | The case has been filed in the Appellate Tribunal. Arguments are in process. | 11.05.07 | 11.07.07 |

--sd--

EE/ED-4

DELHI DEVELOPMENT AUTHORITY

ELECTRICAL DIVISION NO.-4, ROHINI, DELHI-110085.

REPORT OF COURT CASES PERTAINING TO SERVICE MATTER FOR THE MONTH ENDING

| S.NO | SUIT NO. | FILE NO. | TITLE OF THE CASE | NAME OF THE COURT | NAME OF PANEL LAWYER | NATURE OF THE CASE | PRESENT POSITION OF THE CASE | Last date of hearing | NEXT DATE OF HEARING |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | CWP 5380 /97 | F21 (298)/97/ HC/ Legal | Sh. Vinod Kumar v/s DDA | Delhi High Court | Smt.Alp-na Poddar | Conversion from Khallasi to P.O Cadre | Case admitted for regular hearing | -- | Date not yet fixed |
| 2 | CWP 4970 /94 | F2 (296)/95/ HC/ Legal | Sh. Satish Kumar v/s DDA | Delhi High Court | Sh.Rajiv Bansal | (---do---) | (---do---) | -- | (---do---) |
| 3 | CWP 4971 /94 | F2 (297)95/ HC/ Legal | Sh. Roop Chand v/s DDA | Delhi High Court | Sh. Arun Birbal | (---do---) | (---do---) | -- | (---do---) |
| 4 | CWP 1629 /98 | F21 (260)98/HC/ Legal | Sh. Kailash Chand Sharma & Others v/s DDA | Delhi High Court | Sh. Arun Birbal | (---do---) | (---do---) | -- | (---do---) |
| 5 | ID-74/99 | F9 (201)99/TC/Legal | Sh. Rajesh Kumar v/s DDA | Tribunal | Sh. Mukesh Kumar | Conversion from Muster roll period to W/C Cadre | Final arguments concluded. Fresh lawyer to be appointed to get the certified copy of the judgment. DDA file from the previous Lawyer awaited | -- | --- |

-----sd----

Executive Engineer (E)

Electrical Division No.4, DDA,

Rohini, Delhi-110085.

DELHI DEVELOPMENT AUTHORITY

ELECTRICAL DIVISION NO.4, ROHINI, DELHI-110085

DETAILS OF RIS / EIS/ EOT CASES DURING THE YEAR 2007-08 FOR THE QTR. ENDING JUNE’2007

| S.No. | Name of Work | Agency | Agreement No. | Estt. Coat Tendered Amount | Amount of RIS | Amount EIS approved | Details of EOT granted |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Without levy of Compensation | With levy of Compensation |  |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. |
| 1. | C/O 200 LIG Houses in Pkt. I block ‘E’ Sector-18 Rohini (SH:- IEI of 200 DU’s) | M/S Goel Electricals | 06/EE/ ED-4/DDA/ 2005-06 | Rs.16,07,865/- Rs.14,53,464/- | -- | -- | Yes | N/A |  |
| 2. | M/O Completed Schemes under Nazul A/C-II of S.W.Z (SH: - S/I of additional submersible pump set alongwith service cable at Ajay Park & Masodabad Park Najafgarh | M/S Hindustan Enterprises | 106/EE/ ED-4/DDA/ 2005-06 | Rs.1, 59,203/- Rs.1, 34,736/- | -- | -- | Yes | N/A |  |

DELHI DEVELOPMENT AUTHORITY

ELECTRICAL DIVISION NO.-4, ROHINI, DELHI-110085.

# STAUS REPORT OF HANDING OVER OF SERVICES OF 146 COLONIES (BEYOND 382 +163/136 COLONIES) TO D.J.B/M.C.D

| S.NO. | Code No. | Name of Colony | Name of Services | Date of submi- ssion of Comp- letion Plans | Date of Joint Inspection | Amount of Deficiency Estimate | Deficiency amount paid |  |  | Date of Physical Handing Over | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Letter No. | Amount | Cheque No., date & name of Bank |  |  |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12. |
| ## ROHINI ZONE |  |  |  |  |  |  |  |  |  |  |  |
| 1. | RZ-04-02-063 | 480 SFS Cat. II Pkt. 10 Sector-11 Rohini Extn. | (a). Tube Wells (Clear water) | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (b). Booster Pumps | -- | 4.10.05 |  |  |  |  |  | Joint inspect5ion done. Deficiency Estimate amounting to Rs.2,83,000/- collected from DJB is yet to be mutually agreed. |
|  |  |  | (c). SPS | -- | N/A | -- | -- | -- | -- | -- | -- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12. |
|  |  |  | (d). Hort. Pumps | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (e).St. Ltg. | -- | 8.02.05 | Nil |  | Nil |  | 8.02.05 | St. Ltg points handed over EE(E)/MCD General Wing |
| 2. | RZ-04-02-064 | 520(770) MIG Block C&D Sector-18 Rohini | (a). Tube Wells (Clear water) | -- | 4.10.05 |  |  |  |  |  | Joint inspection done. Deficiency Estimate amounting to Rs.3, 07,834/- collected from DJB is yet to be mutually agreed. |
|  |  |  | (b). Booster Pumps |  |  |  |  |  |  |  |  |
|  |  |  | (c). SPS | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (d). Hort. Pumps | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (e).St. Ltg. | -- | 8.02.05 | Nil | -- | Nil | -- | 8.02.05 | St. Ltg points handed over EE(E)/MCD General Wing |
| 3. | RZ-04-06-071 | Periperial Services in Sector18 Rohini | (a). Tube Wells (Clear water) | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (b). Booster Pumps | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (c). SPS | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (d). Hort. Pumps | -- | N/A | -- | -- | -- | -- | -- | -- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12. |
|  |  |  | (e).St. Ltg. | -- | 1.05.06 | Nil | -- | Nil | -- |  | Joint inspection done but St. ltg of left out portion of Sector-18 Rohini M.P Road is yet to be taken over by PWD(Delhi Admn.) |
| 4. | RZ-04-09-080 | C/O 448 SFS in Blk. ‘E’ Sector-18 Rohini | (a). Tube Wells (Clear water) | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (b). Booster Pumps | -- | H/O to DJB | Rs.45,900/- | -- | Rs.45,900/- | -- | 30.03.01 | Booster Pumps handed over to DJB on 30.03.01 |
|  |  |  | (c). SPS | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (d). Hort. Pumps | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (e).St. Ltg. | -- | 8.02.05 | Nil | -- | Nil | -- | 8.02.05 | St. Ltg points handed over EE(E)/MCD General Wing |
| 5. | RZ-04-09-081 | C/O 432 LIG in Pkt. 5 to 8 Sector-18 Rohini | (a). Tube Wells (Clear water) | -- | H/O to DJB | Rs.23,500/- | -- | Rs.23,500/- | -- | 30.03.01 | Booster Pumps handed over to DJB on 30.03.01 |
|  |  |  | (b). Booster Pumps |  |  |  |  |  |  |  |  |
|  |  |  | (c). SPS | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (d). Hort. Pumps | -- | N/A | -- | -- | -- | -- | -- | -- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12. |
|  |  |  | (e).St. Ltg. | -- | 20.10 .93 | Nil | -- | Nil | -- | 20.10.93 | St. Ltg points handed over EE(E)/MCD General Wing |
| 6. | RZ-04-10-096 | 282/286 incremental houses in Pkt. 1 Sector-25 Rohini | (a). Tube Wells (Clear water) | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (b). Booster Pumps | -- | 4.10.05 |  |  |  |  |  | Joint inspection done. Deficiency Estimate amounting to Rs.1, 83,336/- collected from DJB is yet to be mutually agreed |
|  |  |  | (c). SPS | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (d). Hort. Pumps | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (e).St. Ltg. | -- | 8.02.05 | Nil | -- | Nil | -- | 8.02.05 | St. Ltg points handed over EE (E)/MCD General Wing |
| 7. | RZ-04-10-097 | 126/125incremental houses in Pkt. 8 Sector-25 Rohini | (a). Tube Wells (Clear water) | -- | N/A | -- | -- | -- | -- | -- | -- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12. |
|  |  |  | (b). Booster Pumps | -- | 4.10.05 |  |  |  |  |  | Joint inspection done. Combined Deficiency Estimate collected from DJB for Pkt. 8&9 pump sets i.e. for Colony Code No. RZ-04-10-097 & 098 is yet to be mutually agreed |
|  |  |  | (c). SPS | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (d). Hort. Pumps | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (e).St. Ltg. | -- | 8.02.05 | Nil | -- | Nil | -- | 8.02.05 | St. Ltg points handed over EE(E)/MCD General Wing |
| 8. | RZ-04-10-098 | 126/125 incremental houses in Pkt. 9 Sector-25 Rohini | (a). Tube Wells (Clear water) | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (b). Booster Pumps | -- | 4.10.05 |  |  |  |  |  | Joint inspection done. Combined Deficiency Estimate collected from DJB for Pkt. 8&9 pump sets i.e for Colony Code No. RZ-04-10-097 & 098is yet to be mutually agreed |
|  |  |  | (c). SPS | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (d). Hort. Pumps | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (e).St. Ltg. | -- | 8.02.05 | Nil | -- | Nil | -- | 8.02.05 | St. Ltg points handed over EE(E)/MCD General Wing |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12. |
| 9. | RZ-04-10-100 | Peripherail Sewerage Sector23 to 25 Rohini | (a). Tube Wells (Clear water) | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (b). Booster Pumps | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (c). SPS | -- | 4.10.05 |  |  |  |  |  | Joint inspection done. Deficiency Estimate amounting to Rs.14, 52,643/- collected from DJB is yet to be mutually agreed |
|  |  |  | (d). Hort. Pumps | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (e).St. Ltg. | -- | N/A | -- | -- | -- | -- | -- | -- |
| 10. | RZ-04-12-108 | C/O 112 LIG houses in Pkt. ‘A’ Sector-2 Rohini | (a). Tube Wells (Clear water) | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (b). Booster Pumps | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (c). SPS | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (d). Hort. Pumps | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (e).St. Ltg. | -- | 8.02.05 | Nil | -- | Nil | -- | 8.02.05 | St. Ltg points handed over EE(E)/MCD General Wing |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12. |
| 11. | RZ- | Services of Block ‘E’ Sector-1 Avantika Rohini | (a). Tube Wells (Clear water) | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (b). Booster Pumps | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (c). SPS | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (d). Hort. Pumps | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (e).St. Ltg. | -- | 11.11. 05 | Nil | -- | Nil | -- | 11.11. .05 | St. Ltg points handed over EE(E)/MCD General Wing |
| ## SOUTH WEST ZONE |  |  |  |  |  |  |  |  |  |  |  |
| 12 | SWZ-04 WD1—017 | C/O 160/144 CSP Houses at Mianwali CHBS | (a). Tube Wells (Clear water) | -- | 5.10.05 |  |  |  |  |  | Deficiency Estimate for Rs.84,375/- has been mutually agreed & signed but pump house is yet to be handed over to DJB |
|  |  |  | (b). Booster Pumps |  |  |  |  |  |  |  |  |
|  |  |  | (c). SPS | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (d). Hort. Pumps | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (e).St. Ltg. | -- | 21.06. 06 | Nil | -- | Nil | -- | 21.06.06 | St. Ltg points handed over EE(E)/MCD General Wing |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12. |
| 13 | SWZ-04- WD7-023 | C/O 168 MIG Houses Group I at Peera Garhi Crossing Paschim Vihar | (a). Tube Wells (Clear water) | -- | 5.10.05 |  |  |  |  |  | Combined Deficiency Estimate of Group I & II i.e Colony Code No. SWZ-04- WD7-023 & 024 for Rs. 2 lacs + dept. charges given by DJB but final settlement is yet to be done. |
|  |  |  | (b). Booster Pumps |  |  |  |  |  |  |  |  |
|  |  |  | (c). SPS | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (d). Hort. Pumps | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (e).St. Ltg. | -- | 11.11 05 | Nil | -- | Nil | -- | 12.12.05 | St. Ltg points handed over EE(E)/MCD General Wing |
| 14. | SWZ-04 WD7-024 | C/O 136 MIG Houses Group II at Peeragarhi Crossing Paschim Vihar | (a). Tube Wells (Clear water) | -- | 5.10.05 |  |  |  |  |  | Combined Deficiency Estimate of Group I & II i.e. Colony Code No. SWZ-04- WD7-023 & 024 for Rs. 2 lacs + dept. charges given by DJB but final settlement is yet to be done. |
|  |  |  | (b). Booster Pumps |  |  |  |  |  |  |  |  |
|  |  |  | (c). SPS | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (d). Hort. Pumps | -- | N/A | -- | -- | -- | -- | -- | -- |
|  |  |  | (e).St. Ltg. | -- | 11.11. 05 | Nil | -- | Nil | -- | 12.12.05 | St. Ltg points handed over EE (E)/MCD General Wing |

--sd--

EE(E)/ED-4

DELHI DEVELOPMENT AUTHORITY

ELECTRICAL DIVISION NO.-4, ROHINI, DELHI-110085.

# STAUS REPORT OF HANDING OVER OF 163 COLONIES (BEYOND 382 COLONIES) OF DDA TO D.J.B/M.C.D

| S.NO. | Code No. | Name of Colony | Name of Services | Date of submi- ssion of Comp- letion Plans | Date of Joint Inspection | Amount of Deficiency Estimate | Deficiency amount paid |  |  | Date of Physical Handing Over | Remarks including reference of notification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Letter No. | Amount | Cheque No., date & name of Bank |  |  |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12. |
| 1. | WZ-01-07-003 | 748 Janta houses in Shivaji Enclave (S.W.Z) | i) Booster Pumps | N.A | 17.09.02 | Rs.3, 59,938/- | EE/ED4/W (17) /03-04 /DDA | Rs.3, 59,938/- | 615251 dt. 29.03.04 | Not yet taken over by DJB | Notification issued vide no. D-232/EE (P)-II on dt.26.03.04 of MCD. After H/O of services by Civil Wing, electrical services will be handed over to DJB. Civil deficiencies are yet to be finalized which are likely to be decided early as enquired from civil wing |
|  |  |  | ii). Street Lights | 15.01.03 | 15.01.03 | -- |  |  |  |  | Work of providing streetlights is yet to be completed by BSES, the same shall be handed over to MCD after completion of the same |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12. |
| 2. | WZ-01-07-002 | 325SFS hoses at Nagin Lake in Paschim Vihar | i) Booster Pumps | N.A | Feb.’05 |  |  |  |  |  | Deficiency Estimate received from DJB for Rs.4, 87,190/- on 15.12.05, which is yet to be mutually agreed. with DJB. |
|  |  |  | ii). Street Lights | 15.01.03 | 15.01.03 | -- |  |  |  |  | Street lighting points have been jointly inspected with MCD. Efforts are being made for handing over the same to MCD early. |
| 3. | WZ-01-07-006 | LSC Blk. ‘F’ Bhairon Enclave, Paschim Vihar | Street Lights | -- | -- | Rs.1,69,838/- | ED4/W(17)04/DDA/683 dt.30.06.04 | Rs.1,69,838/- | 104008 dt. 03.06.04 |  | Deficiency paid to MCD by DDA as Street Lighting Points were not provided by erstwhile DVB because St. ltg. was not covered in the Estimate of External Electrification Scheme |
| 4. | WZ-01-07-007 | LSC Blk. ‘D’ Indera Enclave, Paschim Vihar | Street Lights | 15.01.03 | 15.01.03 | -- |  |  |  |  | Work of Street Lighting is yet to be completed by BSES. Handing over of st. ltg. points will therefore be taken up after completion of st. ltg. Work |

--sd--

EE/ED-4