PRESENT     STATUS       OF       WORKS    AS     ON      AUGUST – 2007

( SOUTH WEST ZONE )

| S.No. | Name of Work | AA & ES | Progress | Remarks |
| --- | --- | --- | --- | --- |
| 1 | 2 |  | 4 | 5 |
| 1 | C/o Mega Housing Project (2304/2252 HIG/MIG/LIG) at Vasant Kunj, Sec.D,Pkt.6 i)Group-I(252 HIG +104 MIG+120 LIG | A/A & E/S Accorded dated 5.11.2001 for Rs. 2208.07 lacs | 16.5% | Tenders received are being awarded |
|  | ii) Group-II(252 HIG +104 MIG +120 LIG |  | 13% | ---do--- |
|  | iii) Group-III(252 HIG +104 MIG +120 LIG |  | 10% | ---do--- |
|  | iv) Group-IV(252 HIG +104 MIG +120 LIG |  | 11% | ---do--- |
| 2 | ### MEGA HOUSING C/o 436 MIG/LIG houses at Vasant Kunj at Mehrauli Mahipalpur Road near Spinal Injury Hospital. a)311 MIG, 125 LIG | A/A & E/S accorded for Rs. 7724 lacs dated 15.3.2002 | 3% | ---do--- |
|  | ### b)C/o 416 HIG multi four storeyed houses Vasant Kunj at Mehrauli Road near Sultangarhi Tomb |  | 2% | ---do--- |
| 3 | C/o 850 Mass Housing (170 HIG, 340 MIG & 340 LIG) at Vasant Kunj near Sultan- garhi on Turnkey basis (actual no. of houses to be const -ructed 795 No. (140 HIG,350 MIG & 305 LIG | A/A & E/S accorded for Rs. 4731 lacs dated 24.4.2001 | 80% | Work in Progress |
| 4 | C/O 160 HIG at Vasant Kunj Sec.B Pkt.2 (SWD-4) - 72 HIG,Gr-I b)64 HIG,Gr.II | A/A & E/S accorded for Rs. 807.00 lacs dated 5.10.2001 | --- | Work just started |

PRESENT       STATUS       OF     WORKS      AS     ON      AUGUST- 2007

( SOUTH  WEST   ZONE )

| S.No. | Name of Work | AA & ES | Progress | Remarks |
| --- | --- | --- | --- | --- |
| 1 | 2 |  | 4 | 5 |
| 5 | C/o 860/830 two room houses with Lounge on the East side of Pkt. D-6 at Vasant Kunj i/c internal dev. (Civil & Elect.) 290 DU’s Gr.I 270 DU’s Gr.II 270 DU’s Gr.III | A/A & E/S accorded for Rs. 2848 lacs dated 23.3.2005 | 40% 42% 28% | Work in Progress |
| 6 | D/O land in West of JNU, Vasant Kunj Phase-II ii) C/o 12 lacs capacity of UGR & pump house (Balance Work) iii) P/L Rising Main i/c UGR for treated sewerage of V.Kunj Ph-II iv) Improvement of traffic circulation at Nelson Mandela Road & provision of dedicated entry for Shopping Mall | A/A & E/S accorded for Rs. 8376.62 lacs dated 28.2.2001 | 100% 100% 100% | Work Completed |
| 7 | C/o 362 MIG/LIG houses at Mehrauli Mahipalpur near Sultangarhi. (94 LIG + 268 MIG) | Rs. 29,90,36,456/- dated 07.03.2007 | --- | Modified tenders are being called |
| 8 | D/o Therapy Park near Safdarjung Hospital | Approved AA & ES accorded Rs. 259.00 lacs | --- | Project already placed in EAC meeting & approved in 72 meeting. Out of 31 Acres of land, 2 Acre is under stay and 29 Acres, cases in court. Concept drawing available |
| 9 | D/o park at Vasant Kunj opp. Harizan Basti SWD-1 | PE under process | --- | PE under Process in EM’s & Dir.(Fin.)’s office on 20.2.06 |

PRESENT       STATUS       OF     WORKS      AS     ON      AUGUST- 2007

( SOUTH  WEST   ZONE )

| S.No. | Name of Work | AA & ES | Progress | Remarks |
| --- | --- | --- | --- | --- |
| 1 | 2 |  | 4 | 5 |
| 10 | D/o Aravali Bio Diversity Park SWD-1 | Rs.1590.58 lacs dated 14.3.2005 | --- | Work can be held up due to inter- vention of Central Empowered Committee constituted on he behest of Supreme Court of India is still awaited. |
| 11 | D/o Sultangarhi Heritage area SWD-1 | Approved | --- | The T.S. for 4 estimates has been done, tenders are invited but yet to be awarded. |