Details of Contractor Concluded During the Month of September, 2009

Division  No. SED-11/DDA

| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12. | 13. | 14. | 15. | 16. | 17. | 18. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tender No. | Item nature of work | Made of tender Enquiry | Dt. Of public action of NIT | Type of Bidding (Single/ -two Bid System) | Last Dt. Of receipt of tender | Nos. of tenders recd | Nos. & name of parties not qualified after technical evaluation | Whether contractor awarded to lowest tender evaluated LI | Contract No. & Date | Name of Contract | Name of Contractor | Value of contract | Schedule dt. Of completion of supplies contract | Actual dt. Of start of work | Actual dt. Of completion | Reasons for delay if any | Remarks |
| 79/SED-11/08-09 | Maint work | Item rate | 24.11.08 | Single | 02.12.08 | 2 Nos | N.A | Yes | Agmt. 86 SED-11/ 08-09 | Repair of door closer, floor spring & aluminum door at Vikas Sadan | M/S Civil Constn. Co | 1,02,000,/- | 21.07.09 | 22.01.09 | 20.07.09 | -- | -- |
| 29/SED-11/09-10 | Maint work | Item rate | 03.07.09 | Single | 15.07.09 | 7 Nos | N.A | Yes | Agmt. 25 SED-11/ 09-10 | Repair of damaged boundary wall i.c painting of the area near virat cinema. | M/S Arch Constn. | 90,209,/- | 29.08.09 | 31.07.09 | 24.08.09 | -- | -- |
| 95/SED-11/08-09 | Maint work | Item rate | 31.12.08 | Single | 14.01.09 | 4 Nos | N.A | Yes | Agmt. 97 SED-11/ 08-09 | P/F Retro reflective Board, Big Delinator and Small Delinator etc in both side of Siri Fort Auditorium, approach road leading to Siri Fort Sport Complex and Institutional area. | Shri Jatinder Nath Soni | 7,33,129/- | 13.04.09 | 05.02.09 | 13.04.09 | -- | -- |
| 52/SED-11/08-09 | Maint work | Item rate | 22.08.08 | Single | 29.08.08 | 2 Nos | N.A | Yes | Agmt. 65 SED-11/ 08-09 | Const. of Pedestrian Paths at Shanti Stupa | Shri Harinder Singh | 9,77,449/- | 07.01.09 | 08.11.08 | 16.03.09 | -- | EOT granted without lavy of compensation |
| 104/SED-11/08-09 | Maint work | Item rate | 05.02.09 | Single | 17.02.09 | Single | N.A | Yes | Agmt. 01 SED-11/ 09-10 | Pdg. & laying dense carpeting on outer road between INA and C.V.C. Office | Shri Satiner Kumar | 16,84,353,/- | 27.05.09 | 19.06.09 | 06.07.09 | -- | Do |
| NIQ / SED-11 /08-09 | Architect drawing | Item rate | 15.12.08 | Single | 15.12.08 | Single | N.A | Yes | WO /09 SED-11/ 08-09 | Prepration of Arch drawing on CAD formal power point presentation Vikas Sadan | M/S R. Chadha & Associates | 44,000,/- | 24.02.09 | 05.02.09 | 24.02.09 | -- | -- |
| 36/SED-11/09-10 | Maint work | Item rate | 17.07.09 | Single | 25.07.09 | 2 Nos | N.A | Yes | Agmt. 29 SED-11/ 09-10 | P/F of magnetic water conditioner cum descalent (Magna Power) as Vikas Sadan | M/s Sai Aqua Fresh | 1,49,000/- | 13.09.09 | 30.08.09 | 10.09.09 | -- | -- |
| 31/SED-11/08-09 | Maint work | Item rate | 10.07.08 | Single | 18.07.08 | 6 Nos | N.A | Yes | Agmt. 27 SED-11/ 08-09 | Sweeping of parking area on both side of Siri Fort Auditorium approach roads, leading to Siri Fort Sport Complex and Institutional area | Shri. Mnage Ram | 2,06,590/- | 14.08.09 | 14.08.08 | 25.09.09 | -- | EOT granted without lavy of compensation |
| 24/SED-11/09-10 | Maint work | Item rate | 25.06.09 | Single | 04.07.09 | 6 Nos | N.A | Yes | Agmt. 36 SED-11/ 09-10 | Replacement of old rusted G.I &SCI pipe etc in staff flats at AGVC | Shri Devi Ram | 45,520/- | 10.10.09 | 11.09.09 | Work in progress | -- | -- |
| NIQ-1 / SED-11 /09-10 | Maint work | Item rate | 01.08.09 | Single | 27.08.09 | 2 Nos | N.A | Yes | Agmt. 37 SED-11/ 09-10 | Lifting of Scrap material from Vikas Sadan | M/o B.S. Chawla | Lump-sump | 13.03.10 | 12.09.09 | Work in progress | -- | -- |
| 34/SED-11/09-10 | Maint work | Item rate | 17.07.09 | Single | 250.07.09 | 3 Nos | N.A | Yes | Agmt. 38 SED-11/ 09-10 | C/o internal Mainboles and repair of Sewer line at Vikas Sadan | M/S Varshnay Constn. Co | 84,056/- | 17.10.09 | 18.09.09 | Work in progress | -- | -- |
| 31/SED-11/09-10 | Maint work | Item rate | 04.08.09 | Single | 13008.09 | 3 Nos | N.A | Yes | Agmt. 39 SED-11/ 09-10 | Sweeping of Parking area of both sides of Siri Fort Auditorium, approach road leading to Siri Fort Sport Complex. | Shri Ramesh | 1,15,840/- | 25.09.10 | 26.09.09 | Work in progress | -- | -- |
| 14/SED-11/09-10 | Maint work | Item rate | 15.05.09 | Single | 30.05.09 | 4 Nos | N.A | Yes | Agmt. 40 SED-11/ 09-10 | Renovation of Toilets of C-4 in C-Block at Vikas Sadan | Shri Harinder Singh | 10,35,303/- | 25.11.09 | 26.09.09 | Work in progress | -- | -- |
| 43/SED-11/09-10 | Maint work | Item rate | 28.07.09 | Single | 05.09.09 | 2 Nos | N.A | Yes | Agmt. 41 SED-11/ 09-10 | Supply of drinking water through mechanical tankers in U.G water Tank at Vikas Sadan | Shri Desh Raj Bairwa | 3,16,800/- | 27.12.09 | 28.09.09 | Work in progress | -- | -- |
| 42/SED-11/09-10 | Maint work | Item rate | 19.08.09 | Single | 29.08.09 | 3 Nos | N.A | Yes | Agmt. 49 SED-11/ 09-10 | Removal of Malba/ Carbage from Dust Bin in C- Block Parking Vikas Sadan | Shri Devi Ram | 95,004/- | 03.04.10 | 04.10.09 | Work in progress | -- | -- |